Project Name: Charity Organization

Date Prepared: 15 March 2026 Prepared by: Jana Hassan & Seif Ahmed

# Activity List

The following table lists all leaf-level activities from the Work Breakdown Structure (WBS) for the Charity Organization Website project. These are the lowest-level tasks that must be completed to deliver the project.

| Activity ID | Activity Description | Estimated Duration (days) | Preceding Activities | Activity Owner |
| --- | --- | --- | --- | --- |
| 1 | Project Planning & Scoping | 3 | _ | Project Manager |
| 2 | Team & Resource Management | 2 | 1 | Project Manager |
| 3 | Project Tracking & Stakeholder Reporting | 15 | 1 | Project Manager |
| 4 | Stakeholder Workshops & Requirements Gathering | 4 | 1 | Business Analyst |
| 5 | System Architecture & Database Design | 5 | 4 | System Architect |
| 6 | UI/UX Wireframing & Prototyping | 4 | 4 | UI/UX Designer |
| 7 | Core Infrastructure & Backend Setup | 5 | 5 | Backend Developer |
| 8 | User Authentication & Profile Management Module | 6 | 7 | Backend Developer |
| 9 | Main Dashboard & Management Module (Admin View) | 6 | 8 | Full Stack Developer |
| 10 | User Dashboard (User View) | 5 | 8 | Frontend Developer |
| 11 | Donations Panel | 4 | 10 | Frontend Developer |

| Activity ID | Activity Description | Estimated Duration (days) | Preceding Activities | Activity Owner |
| --- | --- | --- | --- | --- |
| 12 | Content Management System | 5 | 9 | Full Stack Developer |
| 13 | Volunteer & Event Management Module | 5 | 9 | Full Stack Developer |
| 14 | Simulated donation form | 4 | 11 | Backend Developer |
| 15 | Test Planning & Case Development | 3 | 6 | QA Engineer |
| 16 | Unit & Integration Testing | 6 | 8, 9, 10, 11, 12, 13, 14 | QA Engineer |
| 17 | System & User Acceptance Testing (UAT) | 4 | 16 | QA team + stakeholders |
| 18 | Security & Performance Testing | 3 | 16 | Security Engineer |
| 19 | Final testing environment setup | 2 | 17, 18 | DevOps Engineer |
| 20 | Content population & final review | 3 | 19 | Database Administrator |
| 21 | User Training & Documentation | 3 | 20 | Business Analyst |
| 22 | Final presentation & sponsor sign-off | 5 | 21 | Full Project Team |