# Charity Organization

| Project Name | Charity Organization |
| --- | --- |
| Prepared By | Jana Hassan & Seif Ahmed |
| Date Prepared | 15 March 2026 |
| Project Sponsor | UNICEF |
| Version | 1.0 |

Website link: https://fruit-drink-09701047.figma.site/

1. PROJECT CHARTER	3

2. Scope Management Plan	7

3. Schedule Management Plan	8

4. Cost Management Plan	9

5. Quality Management Plan	10

6. Resource Management Plan	12

7. Risk Management Plan	13

8. Communication Management Plan	15

9. Scope baseline	17

10. SCHEDULE BASELINE	23

11. COST BASELINE	26

12. RISK REGISTER & PERFORMANCE BASELINE	28

13. QUALITY METRICS & TRACKING BASELINE	32

14. TEAM RESOURCE & RESPONSIBILITY ASSIGNMENT BASELINE	34

15. COMMUNICATIONS MATRIX & REPORTING BASELINE	37

# PROJECT CHARTER

## Project Purpose & Justification

### Business Need / Problem Statement

Many small charity organizations currently lack a professional, functional digital presence. This operational gap severely limits their capability to:

- Share mission statements and real-world impact stories effectively.

- Secure streamlined, online donations.

- Recruit, vet, and onboard community volunteers.

- Promote upcoming fundraising events and localized projects.

Without a centralized website, community engagement remains low and fundraising capabilities are constrained to traditional, inefficient channels.

### Strategic Alignment

This initiative directly aligns with global and organizational priorities, including:

- Digital Transformation: Moving manual NGO operations to accessible web platforms.

- Community Engagement: Creating friction-free pathways for community service and social responsibility.

- Operational Transparency: Building public trust by providing open insight into charitable funding and impact metrics.

### Expected Benefits

- Increase donation accessibility and reach by 40%.

- Improve volunteer registration and processing efficiency by 50%.

- Establish a modern, structured showcase for organization credibility, upcoming events, and stories.

## Measurable Project Objectives & Success Criteria

- Objective 1 (Timeline): Complete the comprehensive design and front-end development of the charity organization website no later than 21 June 2026.

- Objective 2 (Scope & Integration): Successfully develop and integrate all core web pages (Home, About, Projects, Impact Stories, Donation Form, Volunteer Sign-Up, Events Calendar, Contact Page) with seamless, error-free navigation by 25 May 2026.

- Objective 3 (Performance): Optimize front-end architecture to guarantee page load times remain under 3 seconds on modern desktop browsers (Google Chrome and Microsoft Edge) during quality assurance testing by 15 June 2026.

- Objective 4 (Data Quality): Ensure 100% of online intake forms pass rigid front-end validation rules (handling required fields, email syntax, and phone formats) prior to project presentation on 21 June 2026.

## High-Level Requirements

### Functional Requirements

- Content Delivery: The platform must clearly present the organization's mission, vision, active projects, and impact updates.

- Intake Forms: The system must allow users to submit donation requests and register as organizational volunteers.

- Public Engagement: The platform must display an upcoming events calendar and provide a secure contact mechanism for general public inquiries.

- Navigation: The interface must feature a functional, intuitive navigation menu linking all system pages.

### Non-Functional Requirements

- Performance: Maximum page load speed must not exceed 3 seconds under normal network conditions.

- Usability: The website layout must use responsive design, adapting fluidly across desktop and mobile form factors with high readability.

- Reliability: System navigation must perform with zero broken links or critical front-end script errors during staging and evaluation.

- Security: Forms must utilize front-end input filtering to prevent empty or malformed submissions.

- Compatibility: Cross-browser execution must be smooth and visually consistent on Google Chrome and Microsoft Edge.

## Project Boundaries

### Scope Includes

- UI/UX layout and wireframe design of the web platform.

- Clean semantic coding utilizing HTML5, CSS3, and JavaScript.

- Development of all 8 core functional web pages.

- Full front-end responsive framework execution and form validations.

- Basic backend support architecture to capture and process form data.

- Thorough multi-browser testing and defect resolution.

### Out of Scope

- Live production hosting, deployment, or domain server maintenance.

- Development of standalone native mobile apps (iOS or Android packages).

- Advanced third-party external integrations or deep API architectures.

- Live production payment gateways (all donation processing functions will be simulated for demonstration purposes).

## Summary Milestone Schedule

| Milestone Description | Target Completion Date |
| --- | --- |
| Project Initiation & Charter Approval | 01 April 2026 |
| Requirements Finalization | 07 April 2026 |
| UI/UX Design Sign-Off | 20 April 2026 |
| Core Web Page Development Completed | 25 May 2026 |
| Validation Framework & Form Implementation | 01 June 2026 |
| System Testing & Debugging Finalized | 15 June 2026 |
| Final Submission & Presentation | 21 June 2026 |

## Summary Budget

The total estimated project budget is capped at $4,620.

### Cost Allocation

- UI/UX Design Effort: $1,200

- Front-End Development: $1,800

- Testing & Quality Assurance: $600

- Project Management & Documentation: $400

## Key Stakeholders

- Project Sponsor: UNICEF Representative / Charity Executive Board

- Target Users: General community members, prospective philanthropic donors, and volunteer networks.

- Project Team: Internal Web Design, Development, and Quality Assurance Team.

## Governance, Assumptions, & Constraints

### Project Manager Authority Level

Jana Hassan and Seif Ahmed are granted full operational authority over project planning, task delegation, and execution control. They hold direct permission to assign internal tasks, manage the designated budget allocations, and authorize minor scope adjustments that do not jeopardize the final milestone timeline. Any changes modifying baseline delivery dates or core project scope require formal Sponsor sign-off.

### Assumptions

- All assigned project team members will remain active and available throughout all development cycles.

- Standard IDE tools, front-end environments, and testing labs remain accessible.

- Sponsor feedback cycles will be prompt to prevent schedule bottlenecks.

### Constraints

- Timeline: Rigid, non-negotiable project closure deadline of 21 June 2026.

- Financials: Total project budget is strictly capped at $4,620.

- Technology: Project deliverables are strictly bound to standard web applications; mobile platform development is restricted.

## Exit & Closure Criteria

The project will formally transition to closure once:

- All functional pages and validations are completely built to match technical criteria.

- Quality assurance testing confirms zero critical navigation bugs, broken links, or form processing failures.

- All project management lifecycle artifacts are compiled and submitted.

- Formal acceptance and sign-off are issued by the Project Sponsor.

Signatures

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager | Jana Hassan Seif ahmed | JANA SEIF | 17 MARCH 2026 |
| Project Sponsor | UNICEF | UNICEF | 17 MARCH 2026 |

# Scope Management Plan

- Purpose: This plan defines the process for preparing, maintaining, validating, and controlling the project scope baseline throughout the lifecycle of the Charity Organization web application.

- Scope Definition Process: Detailed scope requirements are derived directly from stakeholder meetings and the Project Charter. These are broken down into measurable technical specifications.

- WBS Creation & Maintenance: The Work Breakdown Structure (WBS) divides project deliverables into manageable work packages. Any modifications to the WBS must be assessed for timeline impact and updated in the WBS Dictionary.

- Scope Validation: Deliverables will be reviewed against acceptance criteria at the end of each development phase. Formal acceptance requires explicit sign-off from the Project Sponsor (UNICEF).

- Scope Change Control: If a change to the scope is requested, the Project Managers (Jana Hassan and Seif Ahmed) will analyze its impact on schedule and budget. Minor adjustments can be approved by the PMs, while major alterations require a formal change request submitted to the Project Sponsor.

# Schedule Management Plan

- Purpose: This plan establishes the criteria and activities for developing, monitoring, and controlling the project schedule for the Charity Organization Digital Platform.

- Scheduling Methodology & Tool: The project utilizes a predictive (Waterfall) scheduling methodology to ensure all academic and sponsor milestones are met sequentially . The scheduling tool used to model the timeline, dependencies, and critical path is Microsoft Project / Jira Software.

- Level of Accuracy and Units of Measure: All task durations are estimated and tracked in hours and mapped directly to standard calendar working days (assuming a standard team velocity across the execution period).

- Schedule Maintenance & Updates: The schedule baseline will be reviewed weekly by the Project Managers (Jana Hassan and Seif Ahmed). Actual progress will be compared against the baseline using percentage-of-completion tracking within Jira.

- Control Thresholds: Variance thresholds are established to manage schedule slippage:

  - Under 3 Days Deviation: Managed internally by task reallocation or minor shifting.

  - 3+ Days Deviation: Triggers immediate corrective action (crashing or fast-tracking non-critical activities).

  - Critical Path Threat: Requires immediate notification to the Project Sponsor (UNICEF) with a formal recovery plan.

- Schedule Change Control Process: Any modification to the approved Schedule Baseline dates must be submitted via a formal Change Request. The impact on cost and scope will be evaluated before being approved by the Sponsor.

# Cost Management Plan

- Purpose: This plan establishes the processes and criteria for planning, structuring, estimating, budgeting, and controlling project costs for the Charity Organization Digital Platform.

- Responsibility & Authority: The Project Managers (Jana Hassan and Seif Ahmed) are directly responsible for managing and reporting project costs throughout the lifecycle. The Project Sponsor (UNICEF) holds sole authority to approve any structural budget changes.

- Costing Rules & Level of Precision: * Estimates are compiled using a Bottom-Up Estimation Method with an acceptable level of accuracy of ±10%.

  - All work hours are rounded to the nearest hour, and financial costs are tracked in USD ($) rounded to the nearest dollar.

  - Earned Value Management (EVM) rules dictate that work packages earn value via a 50/50 rule (50% value earned when work begins, and the remaining 50% earned upon complete deliverable finalization) .

- Control Thresholds & Variance Actions: Project performance is monitored through Earned Value indexes:

  - Schedule Variance (SV): $EV - PV$

  - Cost Variance (CV): $EV - AC$

  - Schedule Performance Index (SPI): $EV / PV$

  - Cost Performance Index (CPI): $EV / AC$

  - Warning State (Yellow Status): An index variance of $\pm0.1$ (Index between 0.8–0.9 or 1.1–1.2) triggers immediate issue analysis by the PMs.

  - Critical State (Red Status): If CPI or SPI drops below 0.8 or exceeds 1.2, it indicates severe inefficiency. The PMs must construct a formal corrective action plan (proposing schedule adjustments, resource reallocations, or scope reductions) within 5 days for Sponsor approval .

- Cost Change Control Process: No unauthorized budget modifications are permitted. Any changes to the approved budget must be formally submitted through a change request authorized by UNICEF, and directly updated within the formal Cost Baseline.

- Reporting Cycle: Cost performance metrics are compiled into a Weekly Cost Report shared directly with the project team and supervisor .

# Quality Management Plan

- Purpose: This plan defines how quality will be planned, managed, and controlled for the Charity Organization project to ensure conformance to requirements and fitness for use.

- Quality Standards: The project conforms to the following standards to achieve written specifications:

  - ISO 9000:2000: Quality is defined as the degree to which inherent characteristics fulfill requirements. All deliverables must fully meet the functional and non-functional requirements defined in the Scope Baseline.

  - Conformance to Requirements: Project processes and products must meet written specifications. All website pages, forms, and features must meet the acceptance criteria defined in the WBS Dictionary.

  - Fitness for Use: The product must be usable as intended by end users, meaning the website must be accessible, responsive, and functional on desktop and mobile browsers (Chrome, Edge).

- Quality Management Processes: The project team will execute three core PMBOK quality processes:

  - Planning Quality Management: Proactive process where quality standards, objectives, metrics, roles, and procedures are defined and approved by UNICEF before development begins. Quality is built in through proper environment setup, team training on coding standards, and a test-driven approach.

  - Managing Quality (Quality Assurance): Proactive process concerned with preventing defects through peer code reviews, coding standard compliance, lean process optimization, benchmarking against similar websites, and a formal quality audit at the end of the Testing phase. Weekly quality meetings ensure continuous improvement.

  - Controlling Quality (Quality Control): Reactive process concerned with detecting and resolving defects. Quality control tools (such as Pareto charts, run charts, and control charts) are applied during testing to monitor results against standards. Defects are logged in Jira, triaged by severity, fixed, and re-tested. Verified deliverables are then submitted for formal UNICEF sign-off.

- Roles & Responsibilities for Quality: * Project Managers (Jana Hassan & Seif Ahmed): Hold ultimate accountability for overall project quality. They facilitate quality planning, review QA/QC reports, lead quality audits, and ensure team adherence to standards.

  - Lead Developer: Responsible for technical quality assurance, ensuring backend code structure, database design, and module integrations follow security and architectural standards. Conducts code reviews and monitors unit testing.

  - Frontend Developer: Responsible for visual and interactive quality, ensuring the UI/UX aligns with wireframes, forms validate inputs correctly, and the platform achieves cross-browser compatibility.

  - Tester / QA: Independent validator responsible for executing test cases, running performance benchmarks, conducting security scans, logging defects in Jira, and verifying that fixes meet acceptance criteria.

  - Project Sponsor (UNICEF): Reviews and approves the Quality Management Plan, participates in User Acceptance Testing (UAT), and provides formal sign-off on final deliverables.

# Resource Management Plan

- Purpose: This plan defines how human and physical resources will be identified, estimated, acquired, developed, managed, and controlled throughout the Charity Organization project lifecycle.

- Resource Classification Strategy: Resources are categorized into two primary fields with distinct acquisition pipelines:

  - Human Resources: Internal project infrastructure consisting of Project Managers (Jana Hassan & Seif Ahmed), 2 Frontend Developers, and 1 Quality Assurance Tester. No outsourcing or external contractors are used.

  - Physical Resources: Technical enablement tools including development hardware, web browsers (Chrome, Edge), and local integrated development environments (IDEs). All tools are pre-existing or free open-source architectures, requiring zero active procurement cycles.

- Team Development & Management (Tuckman's Model): The project team moves through structured operational phases managed via active leadership styles:

  - Forming: Cultivating initial alignment during project kickoff workshops.

  - Storming: Resolving technical approach variances using problem-solving and direct PM mediation.

  - Norming: Standardizing code review protocols, shared documentation rules, and peer feedback habits.

  - Performing: Achieving peak velocity during feature integration and testing cycles.

  - Adjourning: Documenting skill transitions within final closeout reports.

- Resource Controlling Mechanisms: Total work effort is bounded to a maximum team size framework (3–7 members) to secure efficiency. Resource utilization is monitored weekly by comparing actual logged hours against planned estimates within Jira. Any detected overallocation triggers immediate task shifting across non-critical paths via the resource histogram.

# Risk Management Plan

- Purpose: This plan outlines how risk identification, analysis, response strategy formulation, and monitoring loops will be organized and controlled throughout the lifecycle of the Charity Organization project.

- Methodology & Tools: The project team utilizes a blend of structured methodologies across standard intervals:

  - Identification: Brainstorming workshops at phase kickoffs, SWOT Analysis, and expert judgment.

  - Consensus: The Delphi Technique to resolve team disagreements regarding priority rankings.

  - Analysis & Logging: Probability/Impact Matrices for qualitative analysis, Expected Monetary Value (EMV) for quantitative analysis, and a centralized Jira Risk Log acting as the official Risk Register.

- Roles & Responsibilities: Risk management activities are distributed across the project infrastructure to ensure comprehensive oversight:

  - Project Managers (Jana Hassan & Seif Ahmed): Act as Lead Risk Owners; responsible for updating the log weekly, facilitating analysis, and escalating critical items to leadership.

  - Project Sponsor (UNICEF): Approves reserves expenditure, reviews regular escalations, and issues final sign-off on residual risk acceptance.

  - Development & QA Team: Monitor risk triggers within their work packages (backend architecture, UI/UX code compatibility, and defect thresholds) and report anomalies immediately.

- Budget, Schedule, & Reserves Alignment: * Contingency Reserve: $400 (10% of direct costs) is built into the Cost Baseline for pre-identified risks.

  - Management Reserve: $220 (5% of Cost Baseline) is held by UNICEF for unforeseen scope variances.

  - Effort & Tracking: An estimated 15 hours is allocated within the Management work package (WBS 1.1). Risks are reviewed every Thursday. A formal process audit will occur at the end of the Testing phase (~10 June 2026).

- Stakeholder Risk Tolerances: The project maintains a strict risk-averse stance due to UNICEF’s non-profit brand requirements. Escalation thresholds are capped at tight boundaries:

  - Schedule: Milestone slips $>3$ days require immediate escalation.

  - Cost: Cost variance $>400$ ($CPI < 0.90$) triggers a mandatory corrective action plan.

  - Quality: Any critical defect at final delivery forces immediate postponement of closure until resolved.

- Risk Auditing & Workarounds: Formal audits track if process rules were executed correctly. For emergent, unlogged threats, team members will immediately document an event-driven workaround directly into the Jira platform.

- Risk Breakdown Structure (RBS)

Risks are categorized hierarchically across five primary environmental levels:

1.0 Project Risk Environment

1.1 Technical Risk (Requirements, Tech Stack, Quality, Security, Integration)

1.2 Project Management Risk (Schedule, Costs, Scope Creep, Estimation, Planning)

1.3 People Risk (Team Availability, Skill Gaps, Conflicts, Sponsor Engagement)

1.4 Organizational Risk (Priorities, Resource Constraints, Direction Changes, Approvals)

1.5 External Risk (Tool Failures, 3rd Party Dependencies, Infrastructure, Force Majeure)

# Communication Management Plan

- Purpose: This plan guides all project communications for the Charity Organization project to ensure the right information reaches the right people at the right time in a useful format.

- Complexity and Communication Channels: As the number of project stakeholders increases, communication complexity increases exponentially. The total number of channels is calculated using the standard formula:

Number of  Channels  =  n(n-1) / 2

Given n = 6 people (5 core team members consisting of Jana, Seif, Lead Dev, Frontend Dev, and Tester, plus 1 sponsor representative from UNICEF), the project contains exactly 15 unique communication channels, requiring high discipline to avoid information overload.

- Communication Methods and Technologies: The project utilizes three PMBOK-aligned communication methods across dedicated technology platforms:

  - Interactive Communication: Two-way real-time exchanges used for complex decisions, conflict resolution, and weekly status reviews. Technologies include Weekly Video/In-Person Meetings and ad-hoc troubleshooting calls.

  - Push Communication: One-way sender-initiated distribution used for routing formal notifications, finalized documents, and regular logs. Technologies include structured Emails and automated Jira notifications.

  - Pull Communication: Recipient-initiated access to a central informational repository used for baseline data or static reference templates. Technologies include the live Jira Project Board and a Shared Project Document Folder.

- Escalation Path and Conflict Resolution: Issues or communication blockages that cannot be resolved at the immediate team level will follow a structured escalation framework:

  - Level 1 (Team Level): Technical issues, minor task conflicts, or short schedule deviations ($\le 2$ days) are resolved by the Project Managers (Jana Hassan & Seif Ahmed) within 1–2 working days.

  - Level 2 (Management Level): Schedule variances $>5$ days, cost variances $>\$400$, quality failures at phase completions, or high-priority risks are evaluated by the PMs and escalated to UNICEF with an impact analysis within 3 working days.

  - Level 3 (Sponsor Level): Baseline changes, milestone delays, and budget adjustments requiring the use of the Management Reserve ($\$220$) are escalated to UNICEF for a final decision within 2 working days.

- Communicating Bad News: When communicating critical challenges (e.g., missed milestones, cost overruns, or critical bugs), the PMs will deliver the information contextually in real time via interactive communication (never by email alone). The communication must outline the root cause, systemic project impact, and a clear, recommended recovery or mitigation plan. Bad news will be communicated to UNICEF as soon as it is identified rather than waiting for the end of a formal reporting cycle.

Revision Procedures: This plan is a living document reviewed upon stakeholder changes, technology updates, or approved Change Requests. Major updates require formal UNICEF approval, while minor contact revisions require PM sign-off, with updated copies distributed within 2 days.

# Scope baseline

Product Scope Description

The Charity Organization platform is a front-end web application built using HTML, CSS, and JavaScript, supported by basic backend functionality. It provides an intuitive interface to maximize community engagement and bolster organizational credibility. The platform features 8 core pages: Home, About, Projects, Impact Stories, Donation Form, Volunteer Sign-Up, Events Calendar, and a Contact Page. All pages utilize responsive design frameworks for seamless desktop and mobile rendering , with strict front-end validation rules for intake forms.

Project Deliverables

- Functional Charity Website: A fully operational web platform delivering the charity's core mission, narrative, and services to the public.

- Validated Intake Forms: Fully operational online forms allowing users to register as volunteers and submit donation requests.

- Dynamic Content Panels: Dedicated modules displaying upcoming events, active projects, and impact updates.

- Responsive UI/UX Layout: A multi-device compatible front-end interface ensuring optimized rendering across mobile and desktop viewpoints.

- Project Governance Documentation: Comprehensive project management artifacts, including this Scope Baseline, quality test logs, and final closeout packages.

Project Exclusions (Out of Scope)

- Native Mobile Apps: No standalone native iOS or Android apps will be compiled; responsiveness is managed entirely via web browsers.

- Live Server Hosting: Production deployment, domain acquisition, and live hosting services are excluded from current delivery cycles.

- Live Financial Gateways: No active financial processors (e.g., Stripe) will be connected. Financial transactions are simulated purely through front-end mock form validations.

- Advanced Integrations: Deep external API integrations outside of the basic core backend functionality are strictly excluded.

Project Constraints

- Schedule: The final website must be fully finalized and submitted by 21 June 2026.

- Budget: The base project cost is $4,000. Factoring in a 10% contingency reserve ($400) and a 5% management reserve ($220), the total approved project budget is strictly capped at $4,620.

- Resources: The core management team consists of Jana Hassan and Seif Ahmed, collaborating with an internal development and design team. Active participation across all project milestones is mandatory.

- Technology: Limited to standard front-end structures (HTML, CSS, JavaScript) alongside basic data processing backend support.

Project Assumptions

- All project team members will remain available and actively participate in designated development and laboratory review sessions.

- Standard software engineering infrastructure (IDEs, modern testing browsers) will remain fully operational throughout the project.

- Feedback and clarification cycles from UNICEF stakeholders will be prompt to avoid critical path delays.

- The project scope will remain locked down; extra features will not be added without formal approval.

Project Acceptance Criteria

- Timeline & Navigation: All 8 core functional web pages must display functional, error-free navigation paths by 25 May 2026.

- Performance Baseline: Every standalone page layout must achieve a page load execution speed under 3 seconds on Google Chrome and Microsoft Edge platforms by 15 June 2026.

- Form Validation: 100% of data collection interfaces must successfully run front-end syntax checks (covering required elements, phone, and email formatting) by 21 June 2026.

- Quality & Sign-off: System testing must show zero critical navigation or processing errors, backed by formal sponsor acceptance.

Work Breakdown Structure (WBS)

1.0 Charity Organization Website

1.1 Project Management

1.1.1 Project Planning & Scoping

1.1.2 Team & Resource Management

1.1.3 Project Tracking & Stakeholder Reporting

1.2 Requirements & Design

1.2.1 Stakeholder Workshops & Requirements Gathering

1.2.2 System Architecture & Database Design

1.2.3 UI/UX Wireframing & Prototyping

1.3 Platform Development

1.3.1 Core Infrastructure & Backend Setup

1.3.2 User Authentication & Profile Management Module

1.3.3 Main Dashboard & Management Module (Admin View)

1.3.4 User Dashboard (User View)

1.3.5 Donations Panel

1.4 Feature Integration

1.4.1 Content Management System (CMS)

1.4.2 Volunteer & Event Management Module

1.4.3 Simulated Donation Form

1.5 Testing & Quality Assurance

1.5.1 Test Planning & Case Development

1.5.2 Unit & Integration Testing

1.5.3 System & User Acceptance Testing (UAT)

1.5.4 Security & Performance Testing

1.6 Deployment & Launch

1.6.1 Final Testing Environment Setup

1.6.2 Content Population & Final Review

1.6.3 User Training & Documentation

1.6.4 Final Presentation & Sponsor Sign-Off

3.3 WBS Dictionary

| WBS Code | Element Name | Description of Work | Deliverable(s) | Hours | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Project Management | Overseeing all planning, execution, and closure activities. | Project Plan, Status Reports. | 80 | Delivered within 10% of budget and schedule. |
| 1.1.1 | Project Planning & Scoping | Developing foundational project charters, scope baselines, and schedules. | Scope Baseline, Schedule. | 30 | Approved by project sponsor. |
| 1.1.2 | Team & Resource Management | Organizing and monitoring team roles and responsibilities. | Resource Plan, RAM/RACI. | 20 | Confirmed by project sponsor. |
| 1.1.3 | Project Tracking & Reporting | Monitoring progress metrics and generating stakeholder status updates. | Status Reports, Dashboards. | 30 | Delivered weekly with zero open blockers. |
| 1.2 | Requirements & Design | Defining detailed technical requirements and creating interface layouts. | System Design Doc, Prototypes. | 90 | Signed off by core stakeholders. |
| 1.2.1 | Requirements Gathering | Conducting workshops to capture functional and non-functional requirements. | Requirements Document. | 20 | Signed off by project sponsor. |
| 1.2.2 | Architecture & DB Design | Structuring front-end flow, basic backend paths, and data schemas. | Architecture & Data Diagrams. | 25 | Reviewed and approved by tech team. |
| 1.2.3 | UI/UX Wireframing | Designing interactive low and high-fidelity page prototypes. | Interactive Prototype, Style Guide. | 45 | Usability testing score >85%. |
| 1.3 | Platform Development | Core engineering, layout construction, and basic backend programming. | Functional System Source Code. | 200 | Code passes reviews with <5% rework. |
| 1.3.1 | Core Infrastructure Setup | Configuring developer environments and foundational file routing structures. | Configured Dev Environment. | 35 | Operational environment available to all devs. |
| 1.3.2 | Authentication Module | Coding registration, login, and simple user profile states. | Functional Login System. | 45 | Successful user registration and profiles. |
| 1.3.3 | Admin Management Module | Building administrative interface for handling site parameters. | Operational Admin Dashboard. | 50 | Admin can modify platform data error-free. |
| 1.3.4 | User Dashboard View | Developing personalized content layouts and registration records views. | Functional User Dashboard. | 40 | Users can view histories and navigate systems. |
| 1.3.5 | Donations Panel | Engineering administrative overview logs tracking mock user transactions. | Integrated Donations Logging. | 30 | Submissions correctly render within admin views. |
| 1.4 | Feature Integration | Assembling CMS panels, form modules, and validation architectures. | Integrated Platform Features. | 110 | Features map cleanly with zero data loss. |
| 1.4.1 | Content Management System | Setting up publishing parameters for news, metrics, and media tools. | Functional CMS Module. | 45 | Admins can create/edit/delete posts cleanly. |
| 1.4.2 | Volunteer & Event Module | Creating intake mechanics for event sign-ups and public schedules. | Volunteer & Events Engine. | 45 | Successful registrations against live events. |
| 1.4.3 | Simulated Donation Form | Building front-end form validation to process mock transaction workflows. | Mock Form with Field Validation. | 20 | Form validates fields and mock submits safely. |
| 1.5 | Testing & QA | Launching validation strategies to secure product parameters. | Test Execution Reports, Bug Tracker. | 80 | Zero critical or high bugs open at sign-off. |
| 1.5.1 | Test Case Development | Writing testing parameters spanning functional and non-functional fields. | Test Plan & Detailed Scenarios. | 15 | 100% test coverage over core requirements. |
| 1.5.2 | Unit & Integration Testing | Evaluating operational states of standalone elements and paired nodes. | Unit & Integration Logs. | 25 | All unit tests pass with zero critical blocks. |
| 1.5.3 | System & UAT | Driving complete end-to-end evaluation loops with target users. | UAT Sign-off Documentation. | 25 | Minimum 95% pass rate across UAT scripts. |
| 1.5.4 | Security & Performance | Running threat scans and page performance benchmark speed tests. | Security & Performance Audits. | 15 | Zero high gaps; page loads under 3 seconds. |
| 1.6 | Deployment & Launch | Preparing documentation, finalizing reviews, and presenting to stakeholders. | Finished Codebase, Final Delivery. | 60 | Successful presentation and sponsor sign-off. |
| 1.6.1 | Final Testing Env Setup | Building stabilized local server configurations mirroring deployment needs. | Confirmed Staging Infrastructure. | 10 | Environment mirrors target operation metrics. |
| 1.6.2 | Content Population | Importing final images, text narratives, and real data templates. | Populated Production-Ready Site. | 15 | Complete data population; zero filler strings. |
| 1.6.3 | Training & Documentation | Authoring structural manuals and training sponsor administrators. | Training Manuals, Completed Course. | 20 | Sponsor confirms navigation capability. |
| 1.6.4 | Final Presentation & Sign-off | Delivering final performance reviews and obtaining formal close-out sign-off. | Sponsor Closeout Document. | 15 | Successful presentation and |

# SCHEDULE BASELINE

Schedule Baseline Overview

The Schedule Baseline is the approved version of the project timeline, developed from the Work Breakdown Structure (WBS) and duration estimates . The project spans from 15 March 2026 (Initial Document Formatting/Planning) to the final hard deadline of 21 June 2026.

Activity List

| Activity ID | Activity Description | Estimated Duration (days) | Preceding Activities | Activity Owner |
| --- | --- | --- | --- | --- |
| 1 | Project Planning & Scoping | 3 | - | Project Manager |
| 2 | Team & Resource Management | 2 | 1 | Project Manager |
| 3 | Project Tracking & Stakeholder Reporting | 15 | 1 | Project Manager |
| 4 | Stakeholder Workshops & Requirements Gathering | 4 | 1 | Business Analyst |
| 5 | System Architecture & Database Design | 5 | 4 | System Architect |
| 6 | UI/UX Wireframing & Prototyping | 4 | 4 | UI/UX Designer |
| 7 | Core Infrastructure & Backend Setup | 5 | 5 | Backend Developer |
| 8 | User Authentication & Profile Management Module | 6 | 7 | Backend Developer |
| 9 | Main Dashboard & Management Module (Admin View) | 6 | 8 | Full Stack Developer |
| 10 | User Dashboard (User View) | 5 | 8 | Frontend Developer |
| 11 | Donations Panel | 4 | 10 | Frontend Developer |
| 12 | Content Management System | 5 | 9 | Full Stack Developer |
| 13 | Volunteer & Event Management Module | 5 | 9 | Full Stack Developer |
| 14 | Simulated donation form | 4 | 11 | Backend Developer |
| 15 | Test Planning & Case Development | 3 | 6 | QA Engineer |
| 16 | Unit & Integration Testing | 6 | 8, 9, 10, 11, 12, 13, 14 | QA Engineer |
| 17 | System & User Acceptance Testing (UAT) | 4 | 16 | QA team + stakeholders |
| 18 | Security & Performance Testing | 3 | 16 | Security Engineer |
| 19 | Final testing environment setup | 2 | 17, 18 | DevOps Engineer |
| 20 | Content population & final review | 3 | 19 | Database Administrator |
| 21 | User Training & Documentation | 3 | 20 | Business Analyst |
| 22 | Final presentation & sponsor sign-off | 5 | 21 | Full Project Team |

Network Diagram

The logical sequencing below outlines task dependencies. Parallel paths represent concurrent activities, while serial dependencies dictate structural bottlenecks.

Critical Path Analysis

The Critical Path is the longest sequence of dependent tasks that determines the shortest possible duration of the project. Any delay to tasks on this path directly shifts the final delivery date.

Requirements Gathering→ UI/UX Design→ Frontend Development→ Backend Development→ Integration→ Testing→ Final Review→ Project Delivery

- Total Float (Slack): Every activity along this primary pathway has a Total Float of 0 days.

- Key Driving Bottlenecks: Designing the administrative framework and establishing the dynamic data paths for donations and content management represent the highest schedule risk to meeting the 21 June 2026 deadline.

Gantt Chart

Is a visual representation of schedule baseline. Red bars within the model represent critical sequence items running continuously to the final milestone, while blue channels illustrate flexible concurrent pipelines

# COST BASELINE

Project Resource Plan

The project budget is driven by selective human capital and essential tool allocations:

| Resource Type | Specific Resource Role | Quantity | Unit Rate | Total Direct Cost |
| --- | --- | --- | --- | --- |
| Human Capital | Front-End Web Developer | 2 | $6.44 / Hour | $3,300 |
| Human Capital | Quality Assurance Tester | 1 | $6.44 / Hour | $550 |
| Equipment/Tools | Integrated Development Environment (IDE) | 1 | Fixed Licensing | $150 |
| Total Direct Cost |  |  |  | $4,000 |

Bottom-Up Cost Estimation Breakdown

Direct costs are calculated at the WBS work package level to secure granular accountability across delivery cycles:

| WBS Code | WBS Element Name / Project Activity | Estimated Hours | Base Labor Rate | Calculated Task Cost |
| --- | --- | --- | --- | --- |
| 1.1 | Project Management | 80 Hours | $6.44 / Hour | $515 |
| 1.2 | Requirements and Design | 90 Hours | $6.44 / Hour | $580 |
| 1.3 | Platform Development | 200 Hours | $6.45 / Hour | $1,290 |
| 1.4 | Feature Integration | 110 Hours | $6.45 / Hour | $710 |
| 1.5 | Testing & Quality Assurance (QA) | 80 Hours | $6.44 / Hour | $515 |
| 1.6 | Deployment and Launch | 60 Hours | $6.50 / Hour | $390 |
| TOTAL | Direct Operational Effort | 620 Hours |  | $4,000 |

Complete Budget & Reserve Structure

To safeguard the project against unforeseen expenses, contingency and management buffers are integrated into the total project budget:

DIRECT ESTIMATED COST

$4,000  + Contingency Reserve (10%): $400 (For identified risks on the register)

COST BASELINE

$4,400 + Management Reserve (5%): $220 (For unforeseen out-of-scope changes)

TOTAL PROJECT BUDGET

$4,620

- Direct Estimated Cost: $4,000 (Sum of all bottom-up work packages).

- Contingency Reserve (10%): $400 allocated under PM authority to manage identified schedule, technical, and scope risks .

- Cost Baseline: $4,400 (The formal, time-phased budget approved for measuring EVM performance).

- Management Reserve (5%): $220 held strictly by the Sponsor (UNICEF) for completely unforeseen changes outside the scope baseline.

- Total Project Budget: $4,620

# RISK REGISTER & PERFORMANCE BASELINE

| Probability \ Impact | Low Impact (1) | Medium Impact (2) | High Impact (3) |
| --- | --- | --- | --- |
| High Probability (3) | 3 — MEDIUM | 6 — HIGH | 9 — HIGH |
| Medium Probability (2) | 2 — LOW | 4 — MEDIUM | 6 — HIGH |
| Low Probability (1) | 1 — LOW | 2 — LOW | 3 — MEDIUM |

Low [1-2], Medium [3-4],  High [6-9].

Negative Risk Register (Threats)

| ID | Rank | Risk Name | Category | Trigger Indicator | P | I | Score | Strategy | Contingency / Fallback Plan | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | 1 | Scope Creep | PM | Unapproved verbal additions | 3 | 3 | 9 | Mitigate | Enforce formal CR process. Use fallback: scope reduction negotiation with UNICEF to protect the 21 June deadline. | Jana Hassan | Open |
| R02 | 2 | Team Unavailability | People | Absent >2 working days | 3 | 3 | 9 | Mitigate | Reassign tasks via RAM. Use fallback: Frontend dev assumes backend tasks, formally revise baseline schedule. | Seif Ahmed | Open |
| R03 | 3 | Schedule Delay | Tech | Weekly SPI < 0.90 | 3 | 2 | 6 | Mitigate | Authorize team overtime; selectively descope non-critical features via schedule contingency buffers. | Jana Hassan | Open |
| R04 | 4 | Budget Overrun | PM | Weekly CPI < 0.90$ | 2 | 3 | 6 | Mitigate | Deploy $400 contingency reserve for known errors; request $220 management reserve for unknown shifts. | Seif Ahmed | Open |
| R05 | 5 | sponsor Feedback Delay | External | No response within 3 days | 2 | 3 | 6 | Mitigate | SLA rule enforcement. Escalate to senior management; adjust schedule via an approved CR if delay exceeds 3 days. | Seif Ahmed | Open |
| R06 | 6 | Late Requirements | PM | CR submitted post-WBS 1.3 | 2 | 2 | 4 | Mitigate | Comprehensive early workshops. Assess CR impact; update baseline; utilize contingency reserve funds. | Jana Hassan | Open |
| R07 | 7 | Integration Failure | Tech | Failure rate >10% in WBS 1.4 | 2 | 2 | 4 | Mitigate | Define clear interfaces early. Allocate extra debugging hours; escalate failures directly to PM. | Lead Dev | Open |
| R08 | 8 | Security Vulnerability | Tech | Critical flaws found in 1.5.4 | 2 | 2 | 4 | Mitigate | Input validation frameworks. Remediate code before final delivery; escalate if fixing requires >3 working days. | Lead Dev | Open |
| R9 | 9 | Tool Unavailability | External | Infrastructure down >1 day | 1 | 3 | 3 | Accept | Rely on local offline development environment setups; restore links within 24 hours and log schedule drift. | Seif Ahmed | Open |

Positive Risk Register (Opportunities)

| ID | Opportunity Name | Description | Category | P | I | Score | Strategy | Response Plan |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| O1 | Early Phase Completion | Development finishes early, providing extra buffer time. | Tech | 2 | 3 | 6 | Exploit | Immediately reallocate saved time into deeper verification testing and UI refinement. |
| O2 | Sponsor Replication | Quality levels trigger UNICEF to replicate product globally. | External | 1 | 3 | 3 | Enhance | Build exhaustive architectural documentation to facilitate seamless future scaling. |
| O3 | Internal Skill Gain | Team captures advanced engineering competencies. | People | 3 | 1 | 3 | Accept | Formally document skills within final closeout reports to build institutional asset bases. |

Weekly Top Ten Risk Item Tracking Snapshot

| Current Rank | Previous Rank | Risk ID | Risk Name | Appearances | Resolution & Progress Summary |
| --- | --- | --- | --- | --- | --- |
| 1 | 1 | R01 | Scope Creep | 4 Weeks | Process strictly enforced; UNICEF formalized CR needs; no out-of-scope code added. |
| 2 | 2 | R02 | Team Unavailable | 4 Weeks | Jira task documentation up to date; developer cross-training complete; log remains open. |
| 3 | 3 | R03 | Schedule Delay | 4 Weeks | Baseline $SPI = 0.95$ (On Track); daily Jira boards active; critical path stable. |
| 4 | 5 | R04 | Budget Overrun | 3 Weeks | Baseline $CPI = 1.00$ (On Budget); contingency reserve remains untouched; rank improved. |
| 5 | 4 | R05 | Poor Code Quality | 4 Weeks | Phase 1.3 peer reviews finalized; zero critical blocks found; rank elevated for integration testing. |
| 6 | 6 | R06 | Feedback Delay | 3 Weeks | 3-day SLA response rule acknowledged by UNICEF; prototype approved on time. |
| 7 | 7 | R07 | Late Requirements | 3 Weeks | Requirements signed off on 25 March 2026; risk trending down; target closure next week. |
| 8 | 8 | R08 | Integration Failure | 2 Weeks | Interfaces defined in systemic designs; testing plan prepared; monitoring active. |
| 9 | 9 | R09 | Security Flaws | 2 Weeks | Guidelines distributed; front-end input validation coding active; scans scheduled for 1.5.4. |
| 10 | 10 | R10 | Tool Unavailable | 2 Weeks | Daily local offline folder backups verified; access credentials safe; risk remains low. |

# QUALITY METRICS & TRACKING BASELINE

Key Quality Metrics

The project team utilizes five distinct operational metrics to quantitatively measure project quality during testing:

| Metric ID | Metric Name | Definition / Calculation Method | Target Baseline Goal | Measurement Frequency |
| --- | --- | --- | --- | --- |
| QM01 | Page Load Speed | Time in seconds for a webpage to fully render on standard desktop browsers under normal network conditions. | < 3.0 Seconds | Weekly during WBS 1.5.4 (Performance Testing). |
| QM02 | Form Validation Rate | Percentage of online intake forms that successfully block empty, malformed, or invalid inputs on the front-end. | 100% Validation Accuracy | Daily during WBS 1.4.3 & 1.5.2 (Integration Testing). |
| QM03 | Defect Density | Number of defects found divided by the total number of website pages ($Defects / 8\ Pages$). | < 2.0 Defects per Page | End of each testing iteration in WBS 1.5. |
| QM04 | Test Case Execution Rate | Percentage of planned test cases successfully executed against the codebase. | 100% Execution Rate | Weekly during WBS 1.5 (System & UAT Testing). |
| QM05 | User Acceptance Pass Rate | Percentage of UAT test scripts completed successfully by the user/sponsor without critical errors. | ≥ 95% Pass Rate | Once, at the conclusion of WBS 1.5.3 (UAT Loops). |

Requirements Traceability Matrix (RTM)

The RTM maps high-level stakeholder requirements through the WBS, technical specifications, and specific test cases to guarantee full delivery verification:

| Requirement No. | Name | Category | Source | Status |
| --- | --- | --- | --- | --- |
| R1 | Website navigation Pages | Functional | Project Charter and stakeholder interviews | Done |
| R2 | Online Donation Form | Functional | UNICEF sponsor requirements and project scope | Done |
| R3 | Volunteer Sign-Up Form | Functional | Stakeholder interviews and project scope | Done |
| R4 | Events Calendar | Functional | Stakeholder interviews and project scope | Done |
| R7 | Content Management System | Functional | Stakeholder interviews and project scope | Done |
| R8 | Simulated Payment Gateway | Functional | Project Charter and UNICEF donation guidelines | Done |

# TEAM RESOURCE & RESPONSIBILITY ASSIGNMENT BASELINE

Roles & Responsibilities Definitions

To secure accountability across delivery pipelines, core organizational responsibilities are assigned as follows:

| Requirement No. | Name | Category | Source | Status |
| --- | --- | --- | --- | --- |
| R5 | Responsive UI/UX design | Design | Project scope statement and UI/UX brief | Done |
| R6 | User Authentication & Profile | Security | Stakeholder interviews and security requirements | Done |
| R9 | Page load Performance | Performance | Project scope statement and performance standards | Done |
| R10 | sponsor acceptance (UNICEF) | Management | Project Charter and UNICEF sponsor sign-off | Done |

- Project Manager (Jana Hassan): Leads comprehensive project planning, schedule modeling, cost tracking, quality oversight, stakeholder communication, change control, and final delivery coordination.

- Project Manager (Seif Ahmed): Co-leads all project management activities, supporting scope validation, schedule adjustments, and cost reporting while coordinating direct reporting interfaces with UNICEF.

- Lead Developer: Owns the end-to-end technical architecture, system design validation, backend configuration logic, and structural feature integrations.

- Frontend Developer: Codes responsive UI/UX layouts, builds form interfaces, integrates content layouts, and executes cross-browser compatibility adjustments.

- Tester / QA: Authors complete test scenarios, logs bugs inside the Jira tracking board, runs performance optimization benchmarks, and validates user acceptance criteria.

Responsibility Assignment Matrix (RAM)

The matrix below contains the RAM requirements. It maps key WBS activities directly to project roles using standard PMI designations:

P = Primary Responsibility, S = Support.

| OBS Units ↓ / WBS Activities → | 1.1 Project management | 1.2 Requirement & Design | 1.3 Platform Developments | 1.4 Feature integration | 1.5 Testing & QA | 1.6 Deploy & Launch |
| --- | --- | --- | --- | --- | --- | --- |
| Project Management | RP | R | R | R | R | RP |
| Design & UX Team |  | RP | P | P |  |  |
| Front-End Dev |  | P | P | P | P | P |
| Back-End Dev |  | P | RP | RP | P | P |
| Quality Assurance |  |  | P | P | RP | P |
| Sponsor (UNICEF) | R | P |  |  | P | R |

RACI

|  | Project Manager (Jana / Seif) | Design & UX | Front-End Dev | Back-End Dev | QA Engineer | Sponsor (UNICEF) |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 Project Planning & Scoping | A | I | I | I | I | C |
| 1.1.2 Team & Resource Management | A | R | R | R | R | I |
| 1.1.3 Project Tracking & Stakeholder Reporting | R | I | I | I | I | A |
| 1.2.1 Stakeholder Workshops & Req. Gathering | A | R | C | C | I | R |
| 1.2.2 System Architecture & Database Design | A | C | C | R | I | I |
| 1.2.3 UI/UX Wireframing & Prototyping | A | R | C | I | I | C |
| 1.3.1 Core Infrastructure & Backend Setup | A | I | C | R | I | I |
| 1.3.2 User Authentication & Profile Management | A | I | R | R | C | I |
| 1.3.3 Main Dashboard — Admin View | A | C | R | R | C | I |
| 1.3.4 User Dashboard — User View | A | C | R | R | C | I |
| 1.3.5 Donations Panel | A | I | R | R | C | I |
| 1.4.1 Content Management System | A | C | R | R | C | I |
| 1.4.2 Volunteer & Event Management Module | A | C | R | R | C | I |
| 1.4.3 Simulated Donation Form | A | R | R | C | C | I |
| 1.5.1 Test Planning & Case Development | A | I | C | C | R | I |
| 1.5.2 Unit & Integration Testing | A | I | R | R | R | I |
| 1.5.3 System & (UAT) | A | I | C | C | R | R |
| 1.5.4 Security & Performance Testing | A | I | C | C | R | I |
| 1.6.1 Final Testing Environment Setup | A | I | R | R | C | I |
| 1.6.2 Content Population & Final Review | A | R | R | C | C | C |
| 1.6.3 User Training & Documentation | R | I | I | I | I | A |
| 1.6.4 Final Presentation & Sponsor Sign-Off | R | I | I | I | I | A |

R = Responsible (does the work), A = Accountable (owns the result), C = Consulted (gives input), I = Informed (kept updated).

Team Charter

To create a collaborative environment and manage interpersonal dynamics throughout the lifecycle, the project team commits to the following behavioral standards:

- Team Values: Integrity, accountability, transparency, mutual respect, and continuous self-improvement.

- Communication Guidelines: Daily progress synchronization updates occur via the Jira task board. Formal project status review adjustments occur every Thursday. Technical blockers are communicated immediately within the shared workspace environment.

- Decision-Making Process: Technical architectural choices are evaluated by the Lead Developer. Scope, cost, and schedule adjustments are authorized by the Project Managers. Irresolvable team deadlocks are settled using the Delphi Technique to secure data-driven team consensus.

- Conflict Resolution Protocol: Interpersonal variances are managed using a Confrontation / Problem-Solving approach. Impacted team roles must address variances privately and objectively. If unresolved within 48 hours, the Project Managers lead standard mediation loops to establish corrective task reallocations.

# COMMUNICATIONS MATRIX & REPORTING BASELINE

Stakeholder Communications Requirements Matrix

The table below defines the explicit information needs, formats, and frequencies mapped to each project role:

| Stakeholder | Project Role | Core Information Needs | Level of Detail | Preferred Delivery Format | Contact Person | Frequency / Due |
| --- | --- | --- | --- | --- | --- | --- |
| UNICEF | Project Sponsor | Milestone progress, cumulative budget performance, risk status, Change Request approvals, deliverable acceptance. | High-level executive summaries with key decisions highlighted. | Written monthly status reports, weekly emails, and formal milestone meetings. | Jana Hassan & Seif Ahmed (PMs). | Monthly formal reports, weekly emails, and ad-hoc milestone meetings. |
| Jana Hassan/ Seif Ahmed | Project Manager | Schedule updates, cost tracking (EVM metrics), quality metrics, open defects, active risks, and team performance. | Full project detail. | Jira dashboards, internal reports, and weekly team meetings. | Jana Hassan (PM) or Seif Ahmed (Co-PM). | Daily Jira tracking and formal weekly Thursday meetings. |
| Lead Developer | Development Team | Task assignments, technical requirements, architecture constraints, integration interfaces, and defect logs. | Technical detail for assigned WBS packages. | Jira task boards and weekly team meetings. | Jana Hassan (PM). | Daily task updates and weekly Thursday meetings. |
| Frontend Dev | Development Team | Task assignments, UI/UX requirements, responsive specifications, design integrations, and bug logs. | Technical detail for assigned WBS packages. | Jira task boards and weekly team meetings. | Jana Hassan (PM). | Daily task updates and weekly Thursday meetings. |
| Tester / QA | Quality Assurance | Test plans, validation scripts, defect tracking logs, test metrics. | Full technical testing and validation detail. | Jira defect log and weekly team meetings. | Seif Ahmed (PM). | Daily defect logging and weekly Thursday meetings. |
| End Users | Beneficiaries / Public | Final website functionality, user guide, volunteer sign-up, and online donation form usage. | User-level context; zero technical or backend jargon. | Live demonstration session and compiled written user guide. | Jana Hassan (PM). | At final project delivery milestone (21 June 2026). |

Communications Distribution Matrix

The project's information flow, production responsibility, and scheduling rules are managed via the following matrix:

| Document Name | Document Format | Content | Level of Detail | Produced By | Received By (Stakeholders) | Due / Frequency |
| --- | --- | --- | --- | --- | --- | --- |
| Weekly Status Report | Written report (email + Jira) + verbal update at weekly meeting | Schedule status (SPI, milestones), cost status (CPI, CV), quality metrics, open defects, risks update, action items from previous week, upcoming activities | Summary with key metrics — enough detail for decision-making | Jana Hassan & Seif Ahmed | Full project team + UNICEF | Every Thursday throughout the project (15 March – 21 June 2026) |
| Monthly Status Report | Formal written hard copy + email attachment + meeting | Cumulative EVM metrics (PV, EV, AC, CV, SV, CPI, SPI, EAC), milestone achievement summary, budget burn rate, top risks, deliverables completed this month, issues and decisions required from sponsor | High-level executive summary — formatted for sponsor audience | Jana Hassan & Seif Ahmed | UNICEF (Project Sponsor) | 1st of each month: April 1, May 1, June 1, 2026 |
| Milestone Completion Report | Written report + formal meeting with UNICEF | Milestone achieved, deliverable description, acceptance criteria met, actual vs. planned date, cost to date, next phase plan | Full project detail at milestone level | Jana Hassan & Seif Ahmed | UNICEF + full project team | At completion of each of the 8 project milestones |
| EVM / Cost Performance Report | Written report + Jira dashboard | PV, EV, AC, CV, SV, CPI, SPI, EAC, TCPI — with trend charts and variance explanation | Full EVM metrics with explanatory narrative | Seif Ahmed (PM) | Jana Hassan, UNICEF | Bi-weekly (every other Thursday) |
| Risk Register Update | Jira risk log + summary table in weekly status report | Updated risk scores, new risks identified, closed risks, top 10 risk tracking list, status of contingency/fallback plans | Full risk register detail in Jira; summary in weekly report | Jana Hassan & Seif Ahmed | Full project team + UNICEF (summary) | Weekly (every Thursday) full register in Jira |
| Defect / Quality Report | Jira defect log + weekly quality review meeting | New defects logged this week, defects fixed, open defects by severity, UAT pass rate, defect trend (run chart), quality metrics vs. targets | Full defect detail in Jira; summary at weekly meeting | Tester / QA | Project Managers + full team | Weekly (every Thursday quality review meeting) |
| Change Request (CR) Report | Formal written CR in Jira + email notification | CR ID, description of requested change, reason, impact analysis (scope, schedule, cost, quality), recommended decision, sponsor approval/rejection | Full impact analysis detail | Any team member (initiator) + PM (impact analysis) | UNICEF (for approval) + full team (for awareness) | As needed — within 2 days of identifying a change need |
| Meeting Minutes | Written document — email distribution | Attendees, agenda items discussed, decisions made, action items (owner + due date), next meeting date | Concise summary — no unnecessary detail | Rotating note-taker (assigned at each meeting) | All meeting attendees + UNICEF (for milestone meetings) | Within 24 hours of each meeting |
| Final Project Report | Formal written document + final presentation (slides) | Project summary, deliverables completed, schedule performance (planned vs. actual), cost performance (final EAC), quality summary, lessons learned, stakeholder sign-off | Complete formal report — executive and technical sections | Jana Hassan & Seif Ahmed | UNICEF + all stakeholders + academic supervisor | 21 June 2026 — project delivery date |
| User Training Materials | Written guide + live demonstration session | How to use the website: donation form, volunteer sign-up, events calendar, contact page — step-by-step instructions for non-technical users | User-friendly; no technical jargon | Jana Hassan (lead) + Frontend Developer | UNICEF staff + end users / community | 21 June 2026 — at final delivery |