## Slide 1
UNICEF SPONSORED
Charity Organization
Website Project
Project Management Final Document
Jana Hassan & Seif Ahmed — 15 March 2026
Website link: https://fruit-drink 09701047.figma.site/

## Slide 2
Project Overview
Business need, objectives & expected impact
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
BUSINESS NEED
▸ No professional digital presence for the charity
▸ Limited fundraising and community engagement
▸ No mechanism for online donation collection
▸ No volunteer recruitment channel
▸ No platform to promote events & projects
EXPECTED IMPACT
+40%
Donation accessibility
+50%
Volunteer registration efficiency
7+
Fully functional website pages
<3s
Page load time target

## Slide 3
Project Charter
Objectives, scope boundaries, milestones & authorization
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
OBJECTIVES
1. Full frontend + backend website by 21 Jun 2026
2. All 8 pages with error-free navigation by 25 May
3. Page load time < 3 seconds (Chrome & Edge)
4. 100% form validation pass rate by 21 Jun 2026
SCOPE BOUNDARIES
✔ IN SCOPE
• HTML/CSS/JS frontend
• Responsive design
• Basic backend support
• Form validation
✘ OUT OF SCOPE
• Native mobile app
• Live hosting
• Real payment gateway
KEY MILESTONES
15 Mar
Charter
Approval
25 Mar
Req's
Approved
10 Apr
Design
Approved
30 Apr
Dev
Complete
25 May
Pages
Done
15 Jun
Testing
Done
21 Jun
Final
Delivery

## Slide 4
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
Project Management Plan (PMP)
Seven subsidiary plans + three baselines — the governance backbone of the project
Scope Management Plan
How scope is defined, validated & controlled. Formal CR process enforced.
Schedule Management Plan
CPM + PERT. 8 milestones. Weekly SPI tracking. Jira + Gantt.
Cost Management Plan
Bottom-up estimation. EVM weekly. $4,620 total budget.
Quality Management Plan
ISO 9000. Control charts, Pareto, defect tracking in Jira.
Resource Management Plan
5-member team. Tuckman model. RAM/RACI defined.
Risk Management Plan
12 risks identified. P×I matrix. Top-10 tracking weekly.
Communication Management Plan
15 channels. Push/Pull/Interactive. Weekly status reports.
THREE BASELINES
Scope Baseline | Schedule Baseline | Cost Baseline ($4,400)

## Slide 5
Scope & Schedule Management Plans
How scope is controlled and schedule is developed
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
SCOPE MANAGEMENT PLAN
Scope Definition
Scope Statement approved by UNICEF before execution
WBS
Top-down decomposition into 6 phases, 20 work packages
Scope Validation
5-step sign-off process with UNICEF at each phase end
Change Control
7-step CR process: Submit → Analyze → UNICEF Approve
Scope Creep Prevention
All reqs in Jira. No informal channels. Formal CR required
SCHEDULE MANAGEMENT PLAN
Method: CPM
Critical Path Method + PERT three-point estimates
Tool: Jira + Gantt
PDM (Finish-to-Start) network diagram
Work Calendar
Sun–Thu, 8 hrs/day, 70 working days total
Performance Metrics
SV = EV−PV | SPI = EV÷PV (target ≥ 0.90)
Control Thresholds
🟢 ≤2 days | 🟡 3–5 days | 🔴 >5 days → escalate

## Slide 6
Cost Management Plan & Budget Breakdown
EVM-based cost control with $4,620 total budget
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
Chart: Cost by WBS Phase (USD)
| Proj Mgmt | Req & Design | Platform Dev | Feature Integ. | Testing & QA | Deployment
Cost ($) | 516 | 581 | 1290 | 710 | 516 | 387
ITEM | AMOUNT
Total Direct Cost (620 hrs × $6.45) | $4,000
Contingency Reserve (10%) | $400
Cost Baseline | $4,400
Management Reserve (5%) | $220
TOTAL PROJECT BUDGET | $4,620
EVM Performance Rules
0/100 rule (≤2 days) • 50/50 rule (3–10 days)
% Complete rule (>10 days) • Review: every Thursday

## Slide 7
Quality & Resource Management Plans
Quality objectives, team structure and development approach
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
QUALITY MANAGEMENT PLAN
Target | Metric | Date
8/8 pages | Error-free navigation | 25 May 2026
< 3 sec | Page load time | 15 Jun 2026
100% | Form validation pass | 21 Jun 2026
0 bugs | Critical defects at delivery | 21 Jun 2026
≥ 95% | UAT test case pass rate | 15 Jun 2026
> 85% | Usability satisfaction score | 10 Apr 2026
RESOURCE MANAGEMENT PLAN
UNICEF (Sponsor)
Jana & Seif (PMs)
Lead Dev
Frontend Dev
Tester/QA
Team Development: Tuckman's 5 Stages
Forming
Storming
Norming
Performing
Adjourning

## Slide 8
Risk Management Plan
Risk register, P×I matrix and top risks
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
PROBABILITY × IMPACT MATRIX
HIGH (3)
3 MED
6 HIGH
9 HIGH
MED (2)
2 LOW
4 MED
6 HIGH
LOW (1)
1 LOW
2 LOW
3 MED
↑ Probability
Impact →
ID | Risk Name | Score | Strategy
R01 | Scope Creep | 9 | Mitigate
R02 | Key Member Unavailability | 9 | Mitigate
R03 | Schedule Delay – Dev Phase | 6 | Mitigate
R04 | Budget Overrun | 6 | Mitigate
R05 | Poor Quality / High Defects | 6 | Mitigate
R06 | UNICEF Feedback Delays | 6 | Mitigate
R10 | Tool Unavailability | 3 | Accept
OPPORTUNITIES:
O1: Early Development Completion → More testing time | O2: UNICEF Replication Opportunity | O3: Team Skill Development

## Slide 9
Communication Management Plan
15 channels, 3 communication methods, structured reporting
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
n(n−1) ÷ 2
6 stakeholders = 15 channels
↔
Interactive
Weekly meetings, milestone reviews, video calls
→
Push
Status reports, meeting minutes, risk register
↓
Pull
Jira board, document folder, WBS artifacts
Communication | Frequency | Audience
Weekly Status Report | Every Thursday | Team + UNICEF
Monthly Sponsor Report | 1st of each month | UNICEF only
EVM Cost Report | Bi-weekly | UNICEF + PMs
Milestone Completion Report | At each milestone | UNICEF + Team
Risk Register Update | Weekly (Thursday) | Team + UNICEF
Change Request Notification | As needed | UNICEF (approval)
Final Project Report | 21 June 2026 | All stakeholders

## Slide 10
Requirements Traceability Matrix (RTM)
Ensuring all requirements are implemented and tested
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
# | Requirement Name | Category | Source | Status
R1 | Website Navigation Pages | Functional | Project Charter | ✔ Done
R2 | Online Donation Form | Functional | UNICEF Requirements | ✔ Done
R3 | Volunteer Sign-Up Form | Functional | Stakeholder Interviews | ✔ Done
R4 | Events Calendar | Functional | Stakeholder Interviews | ✔ Done
R7 | Content Management System | Functional | Stakeholder Interviews | ✔ Done
R8 | Simulated Payment Gateway | Functional | Project Charter | ✔ Done
# | Requirement Name | Category | Source | Status
R5 | Responsive UI/UX Design | Design | Project Scope Statement | ✔ Done
R6 | User Authentication & Profile | Security | Security Requirements | ✔ Done
R9 | Page Load Performance | Performance | Scope / Standards | ✔ Done
R10 | Sponsor Acceptance (UNICEF) | Management | Project Charter | ✔ Done

## Slide 11
Work Breakdown Structure (WBS)
6 phases, 21 work packages — full project decomposition
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
1.0 Charity Organization Website
1.1
Project
Management
Planning & Scoping
Resource Management
Tracking & Reporting
1.2
Requirements
& Design
Stakeholder Workshops & requirement gathering
Architecture & DB
UI/UX Prototyping
1.3
Platform
Development
Core Infrastructure
User Auth
Dashboards
Donations Panel
1.4
Feature
Integration
CMS
Volunteer Module
Donation form
1.5
Testing
& QA
Test Planning
Unit & Integration
System & UAT
Security & Performance
1.6
Deployment
& Launch
Env. Setup
Content population & final review
User Training & documentation
Final presentation & sponsor sign-off

## Slide 12
Activity List
22 scheduled activities with durations, predecessors and owners
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF

## Slide 13
Network Diagram
Precedence Diagramming Method (PDM) — Finish-to-Start dependencies
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF

## Slide 14
Gantt Chart
Project schedule from 15 March to 21 June 2026 (≈70 working days)
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF

## Slide 15
Critical Path Analysis
Longest path = 48 days with zero float — determines project end date
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
Requirements
Gathering (4d)
UI/UX
Design (4d)
Frontend
Dev (5d)
Backend
Dev (6d)
Integration
(5d)
Testing
(6d+4d)
Final
Review (2d)
Delivery
(21 Jun)
Float = 0 days on all critical path activities
~48 working days
Critical Path Duration
70 working days
Project Duration
0 days (zero tolerance)
Float on Critical Path
Daily during execution
Monitoring Frequency

## Slide 16
Responsibility Assignment Matrix (RAM)
Who has Primary (P) and Responsible (R)
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
OBS / WBS | 1.1 Project Management | 1.2 Requirement & Design | 1.3 Platform Development | 1.4 Feature Integration | 1.5 Testing & QA | 1.6 Deploy & Launch
Project Management | RP | R | R | R | R | RP
Design & UX | — | RP | P | P | — | —
Front-End Dev | — | P | P | P | P | P
Back-End Dev | — | P | RP | RP | P | P
Quality Assurance | — | — | P | P | RP | P
Sponsor (UNICEF) | R | P | — | — | P | R
R = Responsible of task | P = Perform the task | RP = Responsible + Primary

## Slide 17
RACI Chart
Responsible = do the task · Accountable · Consulted · Informed
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
I = Informed

## Slide 18
Project Summary
Key metrics, status and deliverables briefly
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF
Project Charter
Approved 17 Mar 2026
Scope Baseline
6 phases · 20 WPs · UNICEF Signed
Schedule Baseline
70 working days · 8 milestones
Cost Baseline
$4,400 · Total Budget $4,620
Requirements
10 requirements · All Done
WBS
6 phases · 20 work packages
Activity List
22 activities · CPM scheduled
Critical Path
~48 days · Zero float
RAM / RACI
5-member team · Roles defined
Risks Identified
12 threats · 3 opportunities
Comm. Channels
15 channels · Weekly reporting

## Slide 19
Thank You
Charity Organization Website Project
Prepared by
Jana Hassan & Seif Ahmed
Sponsor
UNICEF
Deadline
21 June 2026
Questions?
Charity Organization Website | Jana Hassan & Seif Ahmed | UNICEF