Cost Management Plan

Charity Organization

Table of Contents

Introduction	3

Cost Management Approach	3

Measuring Project Costs	4

Reporting Format	6

Cost Variance Response Process	6

Cost Change Control Process	6

Project Budget	6

## 1. INTRODUCTION

The Cost Management Plan clearly defines how the costs on the Charity Organization Website Project will be managed throughout the project’s lifecycle. It sets the format and standards by which project costs are measured, reported, and controlled.

The Cost Management Plan:

- Identifies who is responsible for managing costs

- Identifies who has the authority to approve changes to the project or its budget

- Defines how cost performance is quantitatively measured and reported

- Defines report formats, frequency, and stakeholders

The Project Manager will be responsible for managing and reporting project costs throughout the project duration. During monthly project status meetings, cost performance will be reviewed using Earned Value Management (EVM).

The Project Sponsor (UNICEF) has the authority to approve any budget changes required to keep the project within scope and budget.

## 2. COST MANAGEMENT APPROACH

Costs for this project will be managed at the work package level of the WBS.

Control Accounts (CA) will be created for:

- UI/UX Design

- Front-End Development

- Testing & QA

- Project Management

Earned Value calculations will be used to monitor cost performance.

### Costing Rules

- Work packages earn:

  - 50% value when started

  - 50% upon completion

- Costs rounded to nearest dollar

- Work hours rounded to nearest hour

### Variance Thresholds

- ±0.1 → Warning (Yellow)

- ±0.2 → Critical (Red)

Corrective actions require approval from the Project Sponsor.

## 3. MEASURING PROJECT COSTS

Project cost performance will be measured using Earned Value Management (EVM).

The following metrics will be used:

- Schedule Variance (SV) = EV – PV
Measures if the project is ahead or behind schedule

- Cost Variance (CV) = EV – AC
Measures if the project is under or over budget

- Schedule Performance Index (SPI) = EV / PV
Indicates schedule efficiency

- Cost Performance Index (CPI) = EV / AC
Indicates cost efficiency

### Performance Thresholds

| SPI | 0.9 – 1.1 | <0.8 or >1.2 |
| --- | --- | --- |
| CPI | 0.9 – 1.1 | <0.8 or >1.2 |

If performance exceeds thresholds:

- The Project Manager must analyze the issue

- A corrective action plan must be prepared

## 4. REPORTING FORMAT

Cost performance will be reported through a weekly or bi-weekly project report.

Each report includes:

- Current budget status

- Earned Value metrics (CV, SV, CPI, SPI)

- Identified cost variances

- Planned corrective actions

Reports will be shared with:

- Project team

- Project supervisor

## 5. COST VARIANCE RESPONSE PROCESS

If CPI or SPI falls below 0.8 or exceeds 1.2:

- Project Manager identifies cause

- Corrective actions proposed:

  - Adjust schedule

  - Reallocated resources

  - Reduce scope

- Plan submitted within 5 days

- Sponsor approval required

- Implementation of corrective plan

## 6. COST CHANGE CONTROL PROCESS

All cost changes will follow the project change control process:

- Budget changes must be formally requested

- Changes must be approved by Project Sponsor

- Approved changes to update cost baseline

No unauthorized cost changes are allowed.

## 7. PROJECT BUDGET

1. Cost Management Plan

| Component | Description |
| --- | --- |
| Level of Accuracy | ±10% |
| Units of Measure | USD ($), Hours |
| Estimation Method | Bottom-Up |
| Control Threshold | ±10% |
| Reporting Format | Weekly Cost Report |
| Performance Measurement | EVM |

2. Resource Plan

| Resource Type | Resource | Quantity | Rate | Total Cost |
| --- | --- | --- | --- | --- |
| Human | Developer | 2 | $6.44/hr | $3,300 |
| Human | Tester | 1 | $6.44/hr | $550 |
| Tools | Software/IDE | 1 | fixed | $150 |
|  | total |  |  | $4,000 |

3. Cost Estimation

| WBS Code | Activity | Hours | Rate | Cost |
| --- | --- | --- | --- | --- |
| 1.1. | Project Management | 80 | $6.44 | $515 |
| 1.2 | Requirements and design | 90 | $6.44 | $580 |
| 1.3 | Platform Development | 200 | $6.45 | $1,290 |
| 1.4 | Feature integration | 110 | $6.45 | $710 |
| 1.5 | Testing &QA | 80 | $6.44 | $515 |
| 1.6 | Deployment and launch | 60 | $6.5 | $390 |
| Total |  | 620 |  | $4,000 |

4. Cost Summary

| Type | Amount |
| --- | --- |
| Direct Costs | $4,000 |
| Total Cost | $4,000 |

5. Cost Baseline

| Item | Value |
| --- | --- |
| Total Estimated Cost | $4,000 |
| Contingency Reserve (10%) | $400 |
| Cost Baseline | $4,400 |

6. Total Budget

| Item | Value |
| --- | --- |
| Cost Baseline | $4,400 |
| Management Reserve (5%) | $220 |
| Total Budget | $4,620 |