Critical path analysis

1.Purpose & Overview

The Critical Path Analysis (CPA) is a fundamental project scheduling technique that identifies the longest sequence of dependent activities from project start to project end. This sequence — the Critical Path determines the minimum project duration. Any delay to an activity on the critical path directly delays the project completion date (21 June 2026) by the same number of days. Activities NOT on the critical path have 'float' (also called slack) the amount of time they can be delayed without affecting the project end date.

2. Summary Metrics

| Metric | Value | Notes |
| --- | --- | --- |
| Total Project Duration | 70 working days | 15 March 2026 to 21 June 2026 |
| Critical Path Duration | ~48 working days | Longest sequence — determines project end date |
| Available Float (Non-Critical) | 0 days on critical path | Float on critical path = zero by definition |
| Number of Critical Activities | 11 activities | A1,A4,A5,A7,A8,A9,A12,A16,A17,A19,A20,A21,A22 |
| Number of Non-Critical Activities | 11 activities | Have available float — can be delayed within limits |
| Maximum Available Float | 22 days | Activity A3 (Project Tracking & Reporting) |
| Working Calendar | Sunday – Thursday | 5 days/week, 8 hours/day; Friday & Saturday are non-working |
| Scheduling Method | Critical Path Method (CPM) | Forward and backward pass using Precedence Diagramming Method |
| Float Formula | Total Float = LF – EF | Also = LS – ES |
| Total Activities | 22 | Across 6 WBS phases |
| Total Estimated Hours | 620 hours | Total project effort across all work packages |
| Cost Baseline (BAC) | $4,400 | Direct costs $4,000 + contingency $400 |

3. CPM Methodology

3.1 Forward Pass — Early Dates

The Forward Pass calculates the earliest possible start and finish date for each activity, starting from the project beginning (day 0 = 15 March 2026). For each activity:

Early Start (ES) = the latest Early Finish of all immediate predecessor activities

Early Finish (EF) = Early Start + Duration

For the first activity (no predecessors): ES = 0

3.2 Backward Pass — Late Dates

The Backward Pass calculates the latest allowable start and finish date for each activity without delaying the project end date. Working backwards from the project end:

Late Finish (LF) = the earliest Late Start of all immediate successor activities

Late Start (LS) = Late Finish – Duration

For the last activity: LF = project duration (70 working days)

3.3 Total Float Calculation

Total Float = LF – EF = LS – ES

Total Float = 0: Activity is on the Critical Path. Any delay directly delays the project.

Total Float > 0: Activity is non-critical. It can be delayed by the float value without affecting the project end date.

Negative Float: Would indicate an impossible schedule — all activities in this project have float ≥ 0.

3.4 Dependency Types Used

| Dependency Type | Definition | Example in This Project |
| --- | --- | --- |
| Finish-to-Start (FS) | The predecessor must finish before the successor can start. | A7 (Backend Setup) must finish before A8 (Authentication) can start. |
| Mandatory (Hard Logic) | The sequence is dictated by the technical nature of the work. | A5 (Architecture) must precede A7 (Backend Setup) — code cannot be written before the architecture is designed. |
| Discretionary (Soft Logic) | The sequence is preferred but could theoretically be different. | A15 (Test Planning) follows A6 (UI/UX) testing plans are prepared while development proceeds in parallel. |

4. Critical Path Sequence

The Critical Path is the longest sequence of activities through the project network. All activities on this path have zero Total Float. The critical path for the Charity Organization Website project is:

A1 → A4 → A5 → A7 → A8 → A9 → A12 → A16 → A17 → A19 → A20 → A21 → A22

This sequence represents the following workflow path through the project:

| Step | Activity ID | Activity Name | WBS | Duration | Key Dependency Reason |
| --- | --- | --- | --- | --- | --- |
| 1 | A1 | Project Planning & Scoping | 1.1.1 | 3d | Project start — no predecessor |
| 2 | A4 | Requirements Gathering | 1.2.1 | 4d | Requires A1: Planning must complete first |
| 3 | A5 | System Architecture & DB Design | 1.2.2 | 5d | Requires A4: Architecture follows requirements |
| 4 | A7 | Core Infrastructure & Backend Setup | 1.3.1 | 5d | Requires A5: Backend needs architecture design |
| 5 | A8 | User Authentication & Profile Module | 1.3.2 | 6d | Requires A7: Auth needs infrastructure ready |
| 6 | A9 | Admin Dashboard & Management Module | 1.3.3 | 6d | Requires A8: Dashboard needs auth system |
| 7 | A12 | Content Management System (CMS) | 1.4.1 | 5d | Requires A9: CMS feeds integration testing |
| 8 | A16 | Unit & Integration Testing | 1.5.2 | 6d | Requires A8-A14: All modules must be complete |
| 9 | A17 | System & UAT | 1.5.3 | 4d | Requires A16: Integration testing must pass first |
| 10 | A19 | Final Testing Environment Setup | 1.6.1 | 2d | Requires A17+A18: Both testing phases complete |
| 11 | A20 | Content Population & Final Review | 1.6.2 | 3d | Requires A19: Environment must be ready |
| 12 | A21 | User Training & Documentation | 1.6.3 | 3d | Requires A20: Content must be populated |
| 13 | A22 | Final Presentation & Sponsor Sign-Off | 1.6.4 | 5d | Requires A21: Training must be complete — project end |
| TOTAL |  | Critical Path Duration |  | ~48d | Zero float throughout entire sequence |

5. Non-Critical Activities and Available Float

The following activities have positive Total Float, meaning they can be delayed without impacting the project end date of 21 June 2026. However, if these activities are delayed beyond their available float, they become critical and will extend the project.

| Activity ID | Activity Name | WBS | Duration | Float (days) | Can Be Delayed Until | Risk Note |
| --- | --- | --- | --- | --- | --- | --- |
| A2 | Team & Resource Management | 1.1.2 | 2d | 20d | ~14 Apr 2026 | Low risk — PM activity running parallel to planning |
| A3 | Project Tracking & Reporting | 1.1.3 | 15d | 22d | Throughout project | Low risk — ongoing reporting activity, max float |
| A6 | UI/UX Wireframing & Prototyping | 1.2.3 | 4d | 0d | Cannot be delayed | CRITICAL — feeds test planning (A15) |
| A10 | User Dashboard (User View) | 1.3.4 | 5d | 1d | 1 day only | HIGH RISK — nearly critical; delay = project delay |
| A11 | Donations Panel | 1.3.5 | 4d | 2d | 2 days only | HIGH RISK — nearly critical; feeds simulated form |
| A13 | Volunteer & Event Module | 1.4.2 | 5d | 1d | 1 day only | HIGH RISK — nearly critical; feeds integration testing |
| A14 | Simulated Donation Form | 1.4.3 | 4d | 3d | 3 days only | MEDIUM RISK — monitor weekly |
| A15 | Test Planning & Case Development | 1.5.1 | 3d | 18d | ~04 Jun 2026 | Low risk — can be done well ahead of testing |
| A18 | Security & Performance Testing | 1.5.4 | 3d | 1d | 1 day only | HIGH RISK — converges at A19 with UAT |

Critical Warning: Activities A10, A11, A13, A14, and A18 have very low float (1–3 days). These activities must be treated as nearly critical and monitored daily during execution, not just weekly. Any delay to these activities will immediately move them onto the critical path and delay the project end date.

6. Schedule Control Guidelines

6.1 Control Thresholds (from Schedule Management Plan)

| Status | Condition | Required Action |
| --- | --- | --- |
| Green — On Track | Schedule Variance ≤ ±2 days | No action. Monitor and report status weekly. |
| Yellow — Warning | Schedule Variance of 3–5 days | PM investigates cause. Recovery plan within 3 days. |
| Red — Critical | > 5 days schedule variance | Immediate escalation to UNICEF. Corrective action plan within 2 days. |
| Milestone Slip | Any milestone delayed > 3 days | Immediate escalation. Impact analysis on all downstream milestones. |

6.2 Critical Path Monitoring Approach

Critical path activities (A1, A4, A5, A7, A8, A9, A12, A16, A17, A19, A20, A21, A22) are monitored DAILY during project execution

Near-critical activities (A10, A11, A13, A14, A18 — float 1–3 days) are monitored at every weekly Thursday meeting

SPI (Schedule Performance Index = EV ÷ PV) target: SPI ≥ 0.90 at all times

If SPI drops below 0.90, a corrective action plan is submitted to UNICEF within 3 working days

All schedule changes require a formal Change Request approved by UNICEF before the baseline is updated

6.3 Schedule Recovery Techniques

Crashing: Adding resources to critical path activities to reduce their duration (e.g., adding a second developer to A8 or A9)

Fast-Tracking: Overlapping activities that were originally planned sequentially (e.g., starting A16 testing before all feature integration is complete, if a portion is ready)

Scope Reduction: Removing or simplifying non-essential features to recover schedule — requires UNICEF approval via Change Request

7. Key Schedule Bottlenecks and Risks

| Bottleneck | Why It Is a Risk | Mitigation |
| --- | --- | --- |
| A8 — User Authentication & Profile Module (6d) | The highest-duration activity on the critical path. Feeds A9, A10, and A16 (integration testing). A delay here cascades to all dependent activities. | Assign the most experienced developer. Begin architecture documentation in A5 to enable faster implementation. Monitor daily. |
| A16 — Unit & Integration Testing (6d) | Convergence point for 7 predecessors (A8,9,10,11,12,13,14). All must be complete before A16 can start. One late predecessor delays the entire testing phase. | Track all 7 predecessor activities daily in Jira. Flag any delay immediately. Prepare test cases (A15) well in advance. |
| A9 — Admin Dashboard (6d) | 6-day duration on critical path. Feeds CMS (A12) and Volunteer Module (A13), both of which feed A16. | Peer code reviews at end of each coding day. Escalate blockers immediately. |
| A19 — Final Testing Environment Setup (2d) | Convergence of UAT (A17) and Security Testing (A18). If either is delayed, A19 is delayed, compressing the final delivery timeline. | Monitor A18 daily (only 1 day float). Ensure DevOps engineer is available and environment configuration is pre-planned. |
| 21 June 2026 Deadline | Non-negotiable hard deadline (UNICEF). No extensions possible. | Any SPI < 0.90 triggers immediate corrective action. Daily critical path monitoring in final 2 weeks. |

Appendix A — Full Activity Schedule with CPM Calculations

Charity Organization Website  |  15 March – 21 June 2026  |  All 22 activities  |  Working days: Sunday–Thursday

| Phase 1.1 — Project Management |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Act. ID | Activity Name | WBS Code | Dur. | Pred. | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical? | Activity Owner |
| A1 | Project Planning & Scoping | 1.1.1 | 3d | — | 15 Mar 2026 | 17 Mar 2026 | 15 Mar 2026 | 17 Mar 2026 | 0 | YES | Project Manager |
| A2 | Team & Resource Management | 1.1.2 | 2d | A1 | 18 Mar 2026 | 19 Mar 2026 | 2 Jun 2026 | 3 Jun 2026 | 54 | — | Project Manager |
| A3 | Project Tracking & Reporting | 1.1.3 | 15d | A1 | 18 Mar 2026 | 7 Apr 2026 | 14 May 2026 | 3 Jun 2026 | 41 | — | Project Manager |

| Phase 1.2 — Requirements & Design |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Act. ID | Activity Name | WBS Code | Dur. | Pred. | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical? | Activity Owner |
| A4 | Requirements Gathering | 1.2.1 | 4d | A1 | 18 Mar 2026 | 23 Mar 2026 | 18 Mar 2026 | 23 Mar 2026 | 0 | YES | Business Analyst |
| A5 | System Architecture & DB Design | 1.2.2 | 5d | A4 | 24 Mar 2026 | 30 Mar 2026 | 24 Mar 2026 | 30 Mar 2026 | 0 | YES | System Architect |
| A6 | UI/UX Wireframing & Prototyping | 1.2.3 | 4d | A4 | 24 Mar 2026 | 29 Mar 2026 | 26 May 2026 | 31 May 2026 | 45 | — | UI/UX Designer |

| Phase 1.3 — Platform Development |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Act. ID | Activity Name | WBS Code | Dur. | Pred. | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical? | Activity Owner |
| A7 | Core Infrastructure & Backend Setup | 1.3.1 | 5d | A5 | 31 Mar 2026 | 6 Apr 2026 | 31 Mar 2026 | 6 Apr 2026 | 0 | YES | Backend Developer |
| A8 | User Authentication & Profile Module | 1.3.2 | 6d | A7 | 7 Apr 2026 | 14 Apr 2026 | 7 Apr 2026 | 14 Apr 2026 | 0 | YES | Backend Developer |
| A9 | Admin Dashboard & Management Module | 1.3.3 | 6d | A8 | 15 Apr 2026 | 22 Apr 2026 | 19 Apr 2026 | 26 Apr 2026 | 2 | — | Full Stack Developer |
| A10 | User Dashboard (User View) | 1.3.4 | 5d | A8 | 15 Apr 2026 | 21 Apr 2026 | 15 Apr 2026 | 21 Apr 2026 | 0 | YES | Frontend Developer |
| A11 | Donations Panel | 1.3.5 | 4d | A10 | 22 Apr 2026 | 27 Apr 2026 | 22 Apr 2026 | 27 Apr 2026 | 0 | YES | Frontend Developer |

| Phase 1.4 — Feature Integration |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Act. ID | Activity Name | WBS Code | Dur. | Pred. | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical? | Activity Owner |
| A12 | Content Management System (CMS) | 1.4.1 | 5d | A9 | 23 Apr 2026 | 29 Apr 2026 | 27 Apr 2026 | 3 May 2026 | 2 | — | Full Stack Developer |
| A13 | Volunteer & Event Management Module | 1.4.2 | 5d | A9 | 23 Apr 2026 | 29 Apr 2026 | 27 Apr 2026 | 3 May 2026 | 2 | — | Full Stack Developer |
| A14 | Simulated Donation Form | 1.4.3 | 4d | A11 | 28 Apr 2026 | 3 May 2026 | 28 Apr 2026 | 3 May 2026 | 0 | YES | Backend Developer |

| Phase 1.5 — Testing & QA |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Act. ID | Activity Name | WBS Code | Dur. | Pred. | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical? | Activity Owner |
| A15 | Test Planning & Case Development | 1.5.1 | 3d | A6 | 30 Mar 2026 | 1 Apr 2026 | 1 Jun 2026 | 3 Jun 2026 | 45 | — | QA Engineer |
| A16 | Unit & Integration Testing | 1.5.2 | 6d | A8, A9, A10, A11, A12, A13, A14 | 4 May 2026 | 11 May 2026 | 4 May 2026 | 11 May 2026 | 0 | YES | QA Engineer |
| A17 | System & UAT | 1.5.3 | 4d | A16 | 12 May 2026 | 17 May 2026 | 12 May 2026 | 17 May 2026 | 0 | YES | QA Team + Stakeholders |
| A18 | Security & Performance Testing | 1.5.4 | 3d | A16 | 12 May 2026 | 14 May 2026 | 13 May 2026 | 17 May 2026 | 1 | — | Security Engineer |

| Phase 1.6 — Deployment & Launch |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Act. ID | Activity Name | WBS Code | Dur. | Pred. | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical? | Activity Owner |
| A19 | Final Testing Environment Setup | 1.6.1 | 2d | A17, A18 | 18 May 2026 | 19 May 2026 | 18 May 2026 | 19 May 2026 | 0 | YES | DevOps Engineer |
| A20 | Content Population & Final Review | 1.6.2 | 3d | A19 | 20 May 2026 | 24 May 2026 | 20 May 2026 | 24 May 2026 | 0 | YES | Database Administrator |
| A21 | User Training & Documentation | 1.6.3 | 3d | A20 | 25 May 2026 | 27 May 2026 | 25 May 2026 | 27 May 2026 | 0 | YES | Business Analyst |
| A22 | Final Presentation & Sponsor Sign-Off | 1.6.4 | 5d | A21 | 28 May 2026 | 3 Jun 2026 | 28 May 2026 | 3 Jun 2026 | 0 | YES | Full Project Team |

Legend:

Critical? = YES: Total Float = 0 days. Any delay to this activity directly delays the project end date (21 June 2026).

Total Float: The number of working days an activity can be delayed without impacting the project end date. Formula: LF – EF = LS – ES.

Predecessors: All dependencies use Finish-to-Start (FS) relationships. An activity cannot start until all its predecessors are complete.

Working Days: Sunday through Thursday only. Friday and Saturday are non-working days. Project calendar: 15 March 2026 – 21 June 2026.

Highlighted rows (pink) = Critical Path activities. Activities A10, A11, A13, A14, A18 have 1–3 days float — treat as near-critical.