SCHEDULE BASELINE

1. Purpose and Definition

The Schedule Baseline is the approved version of the project schedule model that can be changed only through formal change control procedures. It is used as a basis for comparison with actual schedule results to measure and manage schedule performance using Earned Value Management (EVM). The Schedule Baseline includes the planned start and finish dates for all activities, the critical path, and all project milestones.

The Schedule Baseline is established and approved by the Project Sponsor (UNICEF) at the end of the Planning phase. Any changes require a formal Change Request approved by UNICEF.

2. Project Calendar and Assumptions

| Parameter | Value |
| --- | --- |
| Project Start Date | 15 March 2026 (Sunday) |
| Project End Date | 21 June 2026 (Sunday) |
| Total Calendar Duration | 99 calendar days |
| Total Working Days | ~70 working days |
| Working Days | Sunday through Thursday (5 days/week) |
| Non-Working Days | Friday and Saturday each week |
| Public Holidays | None assumed during project period |
| Work Hours per Day | 8 hours/day |
| Scheduling Method | Critical Path Method (CPM) — Precedence Diagramming Method (PDM) |
| Dependency Type | Primarily Finish-to-Start (FS) |
| Float Definition | Total Float = LF – EF (days a non-critical activity can be delayed without affecting the project end date) |

3. Project Milestones

| Milestone | Target Date | Description | Status |
| --- | --- | --- | --- |
| M1 — Project Kickoff | 15 Mar 2026 | Project officially starts; Charter and Scope Baseline approved | Baseline |
| M2 — Requirements Approved | 25 Mar 2026 | All functional and non-functional requirements signed off by UNICEF | Baseline |
| M3 — Design Prototype Approved | 10 Apr 2026 | UI/UX wireframes and prototypes approved by stakeholders | Baseline |
| M4 — Core Development Complete | 30 Apr 2026 | All platform development modules (WBS 1.3.x) completed | Baseline |
| M5 — Feature Integration Done | 15 May 2026 | All features (CMS, volunteer module, donation form) integrated | Baseline |
| M6 — All Pages Implemented | 25 May 2026 | All website pages implemented with error-free navigation | Baseline |
| M7 — Testing Complete | 15 Jun 2026 | All testing phases completed; no critical bugs outstanding | Baseline |
| M8 — Final Delivery & Sign-Off | 21 Jun 2026 | Project delivered and formally accepted by UNICEF | Baseline |

4. Critical Path

The Critical Path is the longest sequence of dependent activities that determines the minimum project duration. All activities on the critical path have zero float — any delay will directly delay the project end date.

Critical Path Sequence:

A1 → A4 → A5 → A7 → A8 → A9 → A12 → A16 → A17 → A19 → A20 → A21 → A22

Critical Path Duration: 15 March 2026 → 21 June 2026 = 70 working days

| Critical Path Activity | Duration | Dependency Rationale |
| --- | --- | --- |
| A1 — Project Planning & Scoping | 3 days | Project start — no predecessor |
| A4 — Requirements Gathering | 4 days | Must follow A1 (planning must be complete first) |
| A5 — System Architecture & DB Design | 5 days | Must follow A4 (requirements must be defined) |
| A7 — Core Infrastructure & Backend Setup | 5 days | Must follow A5 (architecture must be designed) |
| A8 — User Authentication & Profile Mgmt | 6 days | Must follow A7 (backend must be set up) |
| A9 — Admin Dashboard | 6 days | Must follow A8 (authentication must exist) |
| A12 — Content Management System | 5 days | Must follow A9 (admin dashboard must exist) |
| A16 — Unit & Integration Testing | 6 days | Must follow A8,9,10,11,12,13,14 (all modules built) |
| A17 — System & UAT | 4 days | Must follow A16 (integration testing complete) |
| A19 — Final Testing Environment Setup | 2 days | Must follow A17 and A18 |
| A20 — Content Population & Final Review | 3 days | Must follow A19 |
| A21 — User Training & Documentation | 3 days | Must follow A20 |
| A22 — Final Presentation & Sponsor Sign-Off | 5 days | Must follow A21 — project end |

5. Schedule Performance Baseline — EVM Reference

The following schedule performance targets are established as part of the Schedule Baseline for EVM monitoring:

| EVM Term | Value | Description |
| --- | --- | --- |
| Schedule Variance (SV) Target | SV ≥ 0 | EV – PV ≥ 0 means on or ahead of schedule |
| Schedule Performance Index (SPI) Target | SPI ≥ 0.90 | Minimum acceptable SPI before corrective action required |
| Schedule Control Threshold — Green | ± 2 days variance | No action required; monitor and report |
| Schedule Control Threshold — Yellow | 3–5 days variance | PM investigates and develops recovery plan within 3 days |
| Schedule Control Threshold — Red | > 5 days variance | Escalate to UNICEF; corrective action plan within 2 days |
| Milestone Slip Threshold | > 3 days | Immediate escalation to UNICEF; impact analysis on all downstream milestones |
| Baseline Review Frequency | Weekly (Thursdays) | Actual start/finish compared to baseline in Jira every Thursday |

6. Schedule Baseline Change Control

| Rule | Detail |
| --- | --- |
| Baseline Authority | Only UNICEF (Project Sponsor) can approve changes to the Schedule Baseline |
| Change Request Process | Any team member may identify a schedule variance; PMs assess impact; UNICEF approves/rejects CR |
| Minor Adjustments | PMs may re-sequence non-critical activities within approved float without a formal CR |
| Critical Path Changes | Any change to a critical path activity requires a formal CR approved by UNICEF |
| Version Control | All versions of the Schedule Baseline are labeled, dated, and stored in Jira |

SCHEDULE BASELINE — Full Activity Schedule with CPM Analysis

Charity Organization Website  |  15 March 2026 – 21 June 2026  |  Working Days: Sunday–Thursday

| Act. ID | Activity Name | Dur. (days) | Pred. | Early Start | Early Finish | Late Start | Late Finish | Total Float | Critical Path? | Activity Owner | WBS Phase |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Planning & Scoping | 3 | — | 15 Mar 2026 | 17 Mar 2026 | 31 Mar 2026 | 2 Apr 2026 | 12 |  | Project Manager | 1.1 |
| 2 | Team & Resource Management | 2 | 1 | 18 Mar 2026 | 19 Mar 2026 | 18 Jun 2026 | 21 Jun 2026 | 66 |  | Project Manager | 1.1 |
| 3 | Project Tracking & Stakeholder Reporting | 15 | 1 | 18 Mar 2026 | 7 Apr 2026 | 1 Jun 2026 | 21 Jun 2026 | 53 |  | Project Manager | 1.1 |
| 4 | Stakeholder Workshops & Requirements Gathering | 4 | 1 | 18 Mar 2026 | 23 Mar 2026 | 5 Apr 2026 | 8 Apr 2026 | 12 |  | Business Analyst | 1.2 |
| 5 | System Architecture & Database Design | 5 | 4 | 24 Mar 2026 | 30 Mar 2026 | 9 Apr 2026 | 15 Apr 2026 | 12 |  | System Architect | 1.2 |
| 6 | UI/UX Wireframing & Prototyping | 4 | 4 | 24 Mar 2026 | 29 Mar 2026 | 11 Jun 2026 | 16 Jun 2026 | 57 |  | UI/UX Designer | 1.2 |
| 7 | Core Infrastructure & Backend Setup | 5 | 5 | 31 Mar 2026 | 6 Apr 2026 | 16 Apr 2026 | 22 Apr 2026 | 12 |  | Backend Developer | 1.3 |
| 8 | User Authentication & Profile Management | 6 | 7 | 7 Apr 2026 | 14 Apr 2026 | 23 Apr 2026 | 30 Apr 2026 | 12 |  | Backend Developer | 1.3 |
| 9 | Main Dashboard & Management Module (Admin) | 6 | 8 | 15 Apr 2026 | 22 Apr 2026 | 5 May 2026 | 12 May 2026 | 14 |  | Full Stack Developer | 1.3 |
| 10 | User Dashboard (User View) | 5 | 8 | 15 Apr 2026 | 21 Apr 2026 | 3 May 2026 | 7 May 2026 | 12 |  | Frontend Developer | 1.3 |
| 11 | Donations Panel | 4 | 10 | 22 Apr 2026 | 27 Apr 2026 | 10 May 2026 | 13 May 2026 | 12 |  | Frontend Developer | 1.3 |
| 12 | Content Management System | 5 | 9 | 23 Apr 2026 | 29 Apr 2026 | 13 May 2026 | 19 May 2026 | 14 |  | Full Stack Developer | 1.4 |
| 13 | Volunteer & Event Management Module | 5 | 9 | 23 Apr 2026 | 29 Apr 2026 | 13 May 2026 | 19 May 2026 | 14 |  | Full Stack Developer | 1.4 |
| 14 | Simulated Donation Form Integration | 4 | 11 | 28 Apr 2026 | 3 May 2026 | 14 May 2026 | 19 May 2026 | 12 |  | Backend Developer | 1.4 |
| 15 | Test Planning & Case Development | 3 | 6 | 30 Mar 2026 | 1 Apr 2026 | 17 Jun 2026 | 21 Jun 2026 | 57 |  | QA Engineer | 1.5 |
| 16 | Unit & Integration Testing | 6 | 8, 9, 10, 11, 12, 13, 14 | 4 May 2026 | 11 May 2026 | 20 May 2026 | 27 May 2026 | 12 |  | QA Engineer | 1.5 |
| 17 | System & User Acceptance Testing (UAT) | 4 | 16 | 12 May 2026 | 17 May 2026 | 28 May 2026 | 2 Jun 2026 | 12 |  | QA Team + Stakeholders | 1.5 |
| 18 | Security & Performance Testing | 3 | 16 | 12 May 2026 | 14 May 2026 | 31 May 2026 | 2 Jun 2026 | 13 |  | Security Engineer | 1.5 |
| 19 | Final Testing Environment Setup | 2 | 17, 18 | 18 May 2026 | 19 May 2026 | 3 Jun 2026 | 4 Jun 2026 | 12 |  | DevOps Engineer | 1.6 |
| 20 | Content Population & Final Review | 3 | 19 | 20 May 2026 | 24 May 2026 | 7 Jun 2026 | 9 Jun 2026 | 12 |  | Database Administrator | 1.6 |
| 21 | User Training & Documentation | 3 | 20 | 25 May 2026 | 27 May 2026 | 10 Jun 2026 | 14 Jun 2026 | 12 |  | Business Analyst | 1.6 |
| 22 | Final Presentation & Sponsor Sign-Off | 5 | 21 | 28 May 2026 | 3 Jun 2026 | 15 Jun 2026 | 21 Jun 2026 | 12 |  | Full Project Team | 1.6 |

Legend:

Critical Path = YES: Zero total float — any delay directly delays the project end date (21 June 2026).

Float > 0: Activity can be delayed by the float value (in working days) without impacting the project end date.

Predecessors: Finish-to-Start (FS) dependency type unless otherwise noted.

Working Days: Sunday through Thursday. Friday and Saturday are non-working days.