# Scope Management Plan

Project Name: Charity Organization

Date Prepared: 15 March 2026

Prepared by: Jana Hassan & Seif Ahmed

## 1. Introduction

The document provides an overview of Scope Baseline for Charity Organization website. It serves as the formal definition of the project scope and will be used as a reference point for managing the project and controlling scope changes. The document includes the Project Scope Statement, WBS, and the WBS Dictionary, which together defines the entire scope of the project.

## 2. Project Scope Statement

### 2.1. Project Justification

Many small charity organizations lack a professional digital presence to:

- Share mission and impact stories

- Collect online donations

- Recruit volunteers

- Promote events and projects

Without an effective website, fundraising and community engagement are limited.

### Strategic Alignment:

This project supports:

- Digital transformation initiatives

- Community engagement and social responsibility

- Increasing transparency in charitable operations

### Expected Benefits:

- Increase donation accessibility by 40%

- Improve volunteer registration efficiency by 50%

- Provide structured showcase for impact stories and events

- Enhance organization credibility and public trust

### 2.2. Product Scope Description

The Charity Organization website will be a comprehensive, front-end web application built using HTML, CSS, and JavaScript with basic backend support. It will enable the organization to present its mission, vision, and impact to the public. The platform’s core functionality will include a Home page, About page, Projects and Impact Stories sections, an online Donation Form, a Volunteer Sign-Up page, an Events Calendar, and a Contact Page. All pages will feature responsive design compatible with both desktop and mobile devices. Front-end form validation will ensure that donation and volunteer submissions are complete and correctly formatted before submission. The system will be designed with a clean, intuitive user interface to ensure high-quality user experience and increase community engagement.

### 2.3. Project Deliverables

- Functional Charity Website: A fully developed and operational web application presenting the charity’s mission and services to the public.

- Donation & Volunteer Forms: Online forms with validation enabling users to submit donation requests and register as volunteers.

- Events & Projects Pages: Dedicated pages showcasing charity projects, impact stories, and an upcoming events calendar.

- Responsive UI/UX Design: A fully responsive design compatible with desktop and mobile devices, ensuring an accessible and visually appealing experience.

- Project Documentation: Complete project management documents including scope baseline, test reports, and final submission documentation.

### 2.4. Project Exclusions

- Native Mobile Application: This project does not include the development of a native iOS or Android application. The website will, however, be mobile-responsive.

- Live Server Hosting & Deployment: Hosting or deploying the website on a live production server is not included in this project.

- Real Payment Gateway Integration: No payment gateway (including Stripe) is integrated. WBS item 1.4.3 covers a simulated donation form only; donations will be simulated and no real financial transactions will be processed.

- Advanced Third-Party Integrations: Implementing advanced third-party integrations beyond core backend functionality is not included in this project.

### 2.5. Constraints

| Constraint Category | Description |
| --- | --- |
| Schedule | The website must be completed and submitted by 21 June 2026, which is the project deadline. |
| Budget | The total estimated cost is $4,000. With a 10% contingency reserve ($400) and 5% management reserve ($220), the total approved budget is $4,620. |
| Resources | The project team consists of Jana Hassan and Seif Ahmed as Project Managers, with a web design and development team. All team members must actively participate in development activities. |
| Technology | The website must be developed using HTML, CSS, and JavaScript for the front-end, with basic backend development. Development tools (IDE, browsers) must be available throughout the project. |

### 2.6. Assumptions

- All team members will actively participate in development activities and attend scheduled lab sessions throughout the project duration.

- Required development tools including HTML, CSS, JavaScript editors, and modern browser (Chrome) will be available to all team members throughout the project.

- Sponsor (UNICEF) feedback will be provided in a timely manner to avoid delays in design and development activities.

- The project scope remains stable and no new features will be added beyond the approved front-end and basic backend scope without formal sponsor approval.

### 2.7. Project Acceptance Criteria

- All defined website pages (Home, About, Projects, Impact Stories, Donation Form, Volunteer Sign-Up, Events Calendar, Contact) must be implemented with error-free navigation by 25 May 2026.

- The website must achieve a maximum page load time of under 3 seconds on standard desktop browsers (Chrome and Edge) during testing by 15 June 2026.

- 100% of donation and volunteer forms must pass front-end validation (required fields, email format, phone format) before final submission by 21 June 2026.

- Final testing must be completed successfully with no critical errors or broken navigation links, and formal acceptance must be received from the Project Sponsor (UNICEF).

## 3. Work Breakdown Structure (WBS)

1.0 Charity Organization Website

1.1 Project Management

1.1.1 Project Planning & Scoping

1.1.2 Team & Resource Management

1.1.3 Project Tracking & Stakeholder Reporting

1.2 Requirements & Design

1.2.1 Stakeholder Workshops & Requirements Gathering

1.2.2 System Architecture & Database Design

1.2.3 UI/UX Wireframing & Prototyping

1.3 Platform Development

1.3.1 Core Infrastructure & Backend Setup

1.3.2 User Authentication & Profile Management Module

1.3.3 Main Dashboard & Management Module (Admin View)

1.3.4 User Dashboard (User View)

1.3.5 Donations Panel

1.4 Feature Integration

1.4.1 Content Management System (Announcements, Reports, Media)

1.4.2 Volunteer & Event Management Module

1.4.3 Simulated Donation Form

1.5 Testing & Quality Assurance

1.5.1 Test Planning & Case Development

1.5.2 Unit & Integration Testing

1.5.3 System & User Acceptance Testing (UAT)

1.5.4 Security & Performance Testing

1.6 Deployment & Launch

1.6.1 Final Testing Environment Setup

1.6.2 Content Population & Final Review

1.6.3 User Training & Documentation

1.6.4 Final Presentation & Sponsor Sign-Off

## 4. WBS Dictionary

| WBS Code | Element Name | Description of Work | Deliverable(s) | Estimated Hours | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Project Management | Overseeing all project activities, including planning, execution, and closure, to ensure the project is delivered on time and within budget. | Project Plan, Status Reports, Budget Tracker | 80 | Project delivered within 10% of budget and schedule. |
| 1.1.1 | Project Planning & Scoping | Creation of all foundational project documents, including the project charter, scope baseline, and detailed project schedule. | Scope Baseline, Project Schedule | 30 | All documents approved by the project sponsor. |
| 1.1.2 | Team & Resource Management | Organizing and managing team roles, responsibilities, and availability throughout the project lifecycle. | Resource Plan, Team Assignment Matrix | 20 | All team roles clearly assigned and confirmed by project sponsor. |
| 1.1.3 | Project Tracking & Stakeholder Reporting | Monitoring project progress against the schedule and budget, and delivering regular status reports to stakeholders. | Status Reports, Progress Dashboard | 30 | Weekly status reports delivered on time with no major unresolved issues. |
| 1.2 | Requirements & Design | Defining the detailed functional and technical requirements of the platform and creating the complete system architecture and user interface design. | System Design Document, UI Prototypes | 90 | Design documents and prototypes approved by stakeholders. |
| 1.2.1 | Stakeholder Workshops & Requirements Gathering | Conducting workshops and interviews with stakeholders to gather, document, and validate all functional and non-functional requirements. | Requirements Document | 20 | Requirements signed off by project sponsor. |
| 1.2.2 | System Architecture & Database Design | Designing the overall system architecture including front-end structure, basic backend setup, and data flow between components. | System Architecture Diagram, Data Flow Diagram | 25 | Architecture reviewed and approved by the project team. |
| 1.2.3 | UI/UX Wireframing & Prototyping | Creating low-fidelity wireframes and high-fidelity interactive prototypes for all user-facing pages of the platform. | Interactive Prototype, Style Guide | 45 | Prototype achieves a user satisfaction score of >85% in usability testing. |
| 1.3 | Platform Development | The core engineering work to build the backend and frontend of the Charity Organization Website, including all major user-facing modules. | Source Code for all Modules | 200 | All code passes review with less than 5% rework. |
| 1.3.1 | Core Infrastructure & Backend Setup | Setting up the development environment, project structure, and basic backend configuration to support all platform modules. | Configured Development Environment, Backend Setup | 35 | Environment is fully operational and accessible to all team members. |
| 1.3.2 | User Authentication & Profile Management | Developing the user authentication system allowing community members to register, log in, and manage their profiles for accessing donation and volunteer features. | Functional User Login & Profile System | 45 | Users can successfully register, log in, and update their profiles. |
| 1.3.3 | Main Dashboard & Management Module (Admin View) | Building the admin-facing dashboard that allows administrators to manage content, users, donations, and events across the platform. | Functional Admin Dashboard | 50 | Admin can view and manage all platform data without errors. |
| 1.3.4 | User Dashboard (User View) | Developing the user-facing dashboard displaying personalized content, donation history, and volunteer activity for registered users. | Functional User Dashboard | 40 | Registered users can view their activity and navigate all dashboard features. |
| 1.3.5 | Donations Panel | Building the donations management panel allowing admins to view and track all simulated donation submissions. | Functional Donations Panel | 30 | All submitted donation records are correctly displayed in the panel. |
| 1.4 | Feature Integration | Integrating key features including the Content Management System, Volunteer & Event Management Module, and Simulated Donation Form. | Integrated Platform Features | 110 | All features are fully functional and integrated without data loss. |
| 1.4.1 | Content Management System | Implementing a system enables admins to publish and manage announcements, impact reports, and media content website. | Functional CMS Module | 45 | Admins can create, edit, and delete content without errors. |
| 1.4.2 | Volunteer & Event Management Module | Developing the module allowing users to sign up as volunteers and view/register for upcoming charity events. | Volunteer Sign-Up & Events Module | 45 | Users can successfully register as volunteers and view all events. |
| 1.4.3 | Simulated Donation Form | Implementing a front-end donation form with full validation. No real payment gateway is integrated; all transactions are simulated only. | Functional Simulated Donation Form | 20 | Form validates required fields and processes simulated submissions successfully. |
| 1.5 | Testing & QA | Executing a comprehensive testing strategy to ensure the platform is robust, secure, and meets all requirements. | Test Reports, Bug Tracker | 80 | No critical or high-severity bugs in production. |
| 1.5.1 | Test Planning & Case Development | Defining the testing strategy and writing detailed test cases covering all functional and non-functional requirements. | Test Plan, Test Cases Document | 15 | Test plan approved and all cases cover 100% of defined requirements. |
| 1.5.2 | Unit & Integration Testing | Testing individual components and their interactions to ensure all modules function correctly in isolation and together. | Unit & Integration Test Reports | 25 | All unit and integration tests pass with no critical failures. |
| 1.5.3 | System & UAT | End-to-end testing of the fully integrated system by the QA team and a select group of end-users. | UAT Sign-off Document | 25 | UAT completed with a 95% pass rate on test cases. |
| 1.5.4 | Security & Performance Testing | Testing the platform for security vulnerabilities and validating that page load times meet the defined acceptance criteria. | Security & Performance Test Report | 15 | No critical security vulnerabilities found; all pages load in under 3 seconds. |
| 1.6 | Deployment & Launch | Completing all final documentation, conducting final testing and bug fixing, obtaining formal sponsor review and acceptance, and presenting the finished charity website. | Completed Website & Final Submission | 60 | Successful final submission with all documents complete and formal sponsor acceptance received. |
| 1.6.1 | Final Testing Environment Setup | Configuring the final local testing environment to simulate the production setup for final review and demonstration. | Configured Testing Environment | 10 | Environment is fully operational and mirrors expected final state. |
| 1.6.2 | Content Population & Final Review | Loading all final content (text, images, events, impact stories) into the website and conducting a full review before submission. | Populated Website, Review Checklist | 15 | All pages contain final content with no placeholder text or broken links. |
| 1.6.3 | User Training & Documentation | Preparing user guides and conducting a brief training session for the sponsor on how to navigate and use the website. | User Guide, Training Session | 20 | Sponsor confirms understanding of website operation. |
| 1.6.4 | Final Presentation & Sponsor Sign-Off | Delivering the final project presentation to the sponsor and stakeholders, demonstrating all website functionality and submitting all required project documentation. | Project Presentation & Sponsor Sign-off | 15 | Presentation delivered successfully and formal acceptance received from Project Sponsor (UNICEF). |

Jira Link:  https://miuegypt-team9.atlassian.net/jira/software/c/projects/CO/boards/37?atlOrigin=eyJpIjoiMjhjZGExYWIzMmE5NGIyYmE4OTAxYWFmNjk1MTk5YjUiLCJwIjoiaiJ9

## 5. Approval and Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager | Jana Hassan Seif ahmed | JANA SEIF | 17 MARCH 2026 |
| Project Sponsor | UNICEF | UNICEF | 17 MARCH 2026 |