## WBS Dictionary

| Code | Element Name | Description of Work | Deliverable(s) | Hrs | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Project Management | Overseeing all project activities, including planning, execution, and closure, to ensure the project is delivered on time and within budget. | Project Plan, Status Reports, Budget Tracker | 80 | Project delivered within 10% of budget and schedule. |
| 1.1.1 | Project Planning & Scoping | Creation of all foundational project documents, including the project charter, scope baseline, and detailed project schedule. | Scope Baseline, Project Schedule | 30 | All documents approved by the project sponsor. |
| 1.1.2 | Team & Resource Management | Organizing and managing team roles, responsibilities, and availability throughout the project lifecycle. | Resource Plan, Team Assignment Matrix | 20 | All team roles clearly assigned and confirmed by project sponsor. |
| 1.1.3 | Project Tracking & Stakeholder Reporting | Monitoring project progress against the schedule and budget and delivering regular status reports to stakeholders. | Status Reports, Progress Dashboard | 30 | Weekly status reports delivered on time with no unresolved issues. |
| 1.2 | Requirements & Design | Defining the detailed functional and technical requirements of the platform and creating the complete system architecture and UI. | System Design Document, UI Prototypes | 90 | Design documents and prototypes approved by stakeholders. |
| 1.2.1 | Stakeholder Workshops & Requirements Gathering | Conducting workshops and interviews with stakeholders to gather, document, and validate all functional and non-functional requirements. | Requirements Document | 20 | Requirements signed off by project sponsor. |
| 1.2.2 | System Architecture & Database Design | Designing the overall system architecture including front-end structure, basic backend setup, and data flow between components. | System Architecture Diagram, DFD | 25 | Architecture reviewed and approved by the project team. |
| 1.2.3 | UI/UX Wireframing & Prototyping | Creating low-fidelity wireframes and high-fidelity interactive prototypes for all user-facing pages of the platform. | Interactive Prototype, Style Guide | 45 | Prototype achieves a user satisfaction in usability testing. |
| 1.3 | Platform Development | The core engineering work to build the backend and frontend of the Charity Organization Website, including all modules. | Source Code for all Modules | 200 | All code passes review with less than 5% rework. |
| 1.3.1 | Core Infrastructure & Backend Setup | Setting up the development environment, project structure, and basic backend configuration to support all platform modules. | Configured Development Environment, Backend Setup | 35 | Environment is fully operational and accessible to all team members. |
| 1.3.2 | User Authentication & Profile Management | Developing the user authentication system allowing community members to register, log in, and manage their profiles for accessing donation and volunteer features. | Functional User Login & Profile System | 45 | Users can successfully register, log in, and update their profiles. |
| 1.3.3 | Main Dashboard & Management Module (Admin View) | Building the admin-facing dashboard that allows administrators to manage content, users, donations, and events across the platform. | Functional Admin Dashboard | 50 | Admin can view and manage all platform data without errors. |
| 1.3.4 | User Dashboard (User View) | Developing the user-facing dashboard displaying personalized content, donation history, and volunteer activity for registered users. | Functional User Dashboard | 40 | Registered users can view their activity and navigate all dashboard features. |
| 1.3.5 | Donations Panel | Building the donations management panel allowing admins to view and track all simulated donation submissions. | Functional Donations Panel | 30 | All submitted donation records are correctly displayed in the panel. |
| 1.4 | Feature Integration | Integrating key features include the Content Management System, Volunteer & Event Management Module, and Simulated Donation Form. | Integrated Platform Features | 110 | All features are fully functional and integrated without data loss. |
| 1.4.1 | Content Management System | Implementing a system enables admins to publish and manage announcements, impact reports, and media content website. | Functional CMS Module | 45 | Admins can create, edit, and delete content without errors. |
| 1.4.2 | Volunteer & Event Management Module | Developing the module allowing users to sign up as volunteers and view/register for upcoming charity events. | Volunteer Sign-Up & Events Module | 45 | Users can successfully register as volunteers and view all events. |
| 1.4.3 | Simulated Donation Form | Implementing a front-end donation form with full validation. No real payment gateway is integrated; all transactions are simulated only. | Functional Simulated Donation Form | 20 | Form validates required fields and processes simulated submissions successfully. |
| 1.5 | Testing & QA | Executing a comprehensive testing strategy to ensure the platform is robust, secure, and meets all requirements. | Test Reports, Bug Tracker | 80 | No critical or high-severity bugs in production. |
| 1.5.1 | Test Planning & Case Development | Defining the testing strategy and writing detailed test cases covering all functional and non-functional requirements. | Test Plan, Test Cases Document | 15 | Test plan approved and all cases cover 100% of defined requirements. |
| 1.5.2 | Unit & Integration Testing | Testing individual components and their interactions to ensure all modules function correctly in isolation and together. | Unit & Integration Test Reports | 25 | All unit and integration tests pass with no critical failures. |
| 1.5.3 | System & UAT | End-to-end testing of the fully integrated system by the QA team and a select group of end-users. | UAT Sign-off Document | 25 | UAT completed with a 95% pass rate on test cases. |
| 1.5.4 | Security & Performance Testing | Testing the platform for security vulnerabilities and validating that page load times meet the defined acceptance criteria. | Security & Performance Test Report | 15 | No critical security vulnerabilities were found; all pages load in under 3 seconds. |
| 1.6 | Deployment & Launch | Completing all final documentation, conducting final testing and bug fixing, obtaining formal sponsor review and acceptance, and presenting the finished charity website. | Completed Website & Final Submission | 60 | Successful final submission with all documents complete and formal sponsor acceptance received. |
| 1.6.1 | Final Testing Environment Setup | Configuring the final local testing environment to simulate the production setup for final review and demonstration. | Configured Testing Environment | 10 | Environment is fully operational and mirrors expected final state. |
| 1.6.2 | Content Population & Final Review | Loading all final content (text, images, events, impact stories) into the website and conducting a full review before submission. | Populated Website, Review Checklist | 15 | All pages contain final content with no placeholder text or broken links. |
| 1.6.3 | User Training & Documentation | Preparing user guides and conducting a brief training session for the sponsor on how to navigate and use the website. | User Guide, Training Session | 20 | Sponsor confirms understanding of website operation. |
| 1.6.4 | Final Presentation & Sponsor Sign-Off | Delivering the final project presentation to the sponsor and stakeholders, demonstrating all website functionality and submitting all required project documentation. | Project Presentation & Sponsor Sign-off | 15 | Presentation delivered successfully and formal acceptance received from Project Sponsor (UNICEF). |

# Work Breakdown Structure (WBS)

1.0 Charity Organization Website

1.1 Project Management

1.1.1 Project Planning & Scoping

1.1.2 Team & Resource Management

1.1.3 Project Tracking & Stakeholder Reporting

1.2 Requirements & Design

1.2.1 Stakeholder Workshops & Requirements Gathering

1.2.2 System Architecture & Database Design

1.2.3 UI/UX Wireframing & Prototyping

1.3 Platform Development

1.3.1 Core Infrastructure & Backend Setup

1.3.2 User Authentication & Profile Management Module

1.3.3 Main Dashboard & Management Module (Admin View)

1.3.4 User Dashboard (User View)

1.3.5 Donations Panel

1.4 Feature Integration

1.4.1 Content Management System (Announcements, Reports, Media)

1.4.2 Volunteer & Event Management Module

1.4.3 Simulated Payment Gateway Integration

1.5 Testing & Quality Assurance

1.5.1 Test Planning & Case Development

1.5.2 Unit & Integration Testing

1.5.3 System & User Acceptance Testing (UAT)

1.5.4 Security & Performance Testing

1.6 Deployment & Launch

1.6.1 Final Testing Environment Setup

1.6.2 Content Population & Final Review

1.6.3 User Training & Documentation

1.6.4 Final Presentation & Sponsor Sign-Off